## Joint Conf
| Mean | Sigma | Distribution | p | q | 1st | 99th
Cost | 100 | 40 | Lognormal | 4.531 | 0.38525 | 37.8915 | 152.1219
Sched | 36 | 12 | Lognormal | 3.5308 | 0.32459 | 16.0502 | 72.6719
Correlation | 0.6 |  |  |  | <---linear correlation between cost/schedule; adjust this value to attain rho correlation value you want for cost/schedule
rho(1,2) | 0.61544 |  |  |  | <---rho is calculated value used for bivariate lognormal, and is the correlation value used in calculations
Results
| Project Budget: |  |  |  |  | 80
| Project Schedule: |  |  |  |  | 30
| Your cost confidence is: |  |  |  |  | 34.95% | <---independent, not taking schedule into account
| Your schedule confidence is: |  |  |  |  | 34.48% | <---independent, not taking cost into account
| Your project has joint cost and schedule confidence equal to: |  |  |  |  | 20.35% | <---probability of achieving both project budget and project schedule
JOINT COST AND SCHEDULE CONFIDENCE TABLE
Sched in Months
|  |  | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100
|  |  | 16.0502 | 16.6164 | 17.1827 | 17.7489 | 18.3151 | 18.8813 | 19.4475 | 20.0137 | 20.58 | 21.1462 | 21.7124 | 22.2786 | 22.8448 | 23.411 | 23.9773 | 24.5435 | 25.1097 | 25.6759 | 26.2421 | 26.8083 | 27.3746 | 27.9408 | 28.507 | 29.0732 | 29.6394 | 30.2056 | 30.7719 | 31.3381 | 31.9043 | 32.4705 | 33.0367 | 33.6029 | 34.1692 | 34.7354 | 35.3016 | 35.8678 | 36.434 | 37.0002 | 37.5665 | 38.1327 | 38.6989 | 39.2651 | 39.8313 | 40.3975 | 40.9638 | 41.53 | 42.0962 | 42.6624 | 43.2286 | 43.7948 | 44.3611 | 44.9273 | 45.4935 | 46.0597 | 46.6259 | 47.1921 | 47.7584 | 48.3246 | 48.8908 | 49.457 | 50.0232 | 50.5894 | 51.1557 | 51.7219 | 52.2881 | 52.8543 | 53.4205 | 53.9867 | 54.553 | 55.1192 | 55.6854 | 56.2516 | 56.8178 | 57.384 | 57.9503 | 58.5165 | 59.0827 | 59.6489 | 60.2151 | 60.7813 | 61.3476 | 61.9138 | 62.48 | 63.0462 | 63.6124 | 64.1786 | 64.7449 | 65.3111 | 65.8773 | 66.4435 | 67.0097 | 67.5759 | 68.1422 | 68.7084 | 69.2746 | 69.8408 | 70.407 | 70.9732 | 71.5394 | 72.1057 | 72.6719
| 0 | 37.8915 | 0.0019833 | 0.0023683 | 0.0027769 | 0.0032029 | 0.0036399 | 0.0040816 | 0.0045222 | 0.0049563 | 0.005379 | 0.0057866 | 0.0061757 | 0.0065439 | 0.0068896 | 0.0072116 | 0.0075096 | 0.0077835 | 0.0080338 | 0.0082613 | 0.008467 | 0.0086521 | 0.008818 | 0.0089659 | 0.0090975 | 0.009214 | 0.0093168 | 0.0094073 | 0.0094868 | 0.0095563 | 0.009617 | 0.0096699 | 0.0097158 | 0.0097557 | 0.0097902 | 0.0098201 | 0.0098458 | 0.009868 | 0.0098871 | 0.0099035 | 0.0099176 | 0.0099297 | 0.00994 | 0.0099489 | 0.0099565 | 0.0099629 | 0.0099684 | 0.0099732 | 0.0099772 | 0.0099806 | 0.0099835 | 0.009986 | 0.0099881 | 0.0099899 | 0.0099914 | 0.0099927 | 0.0099938 | 0.0099947 | 0.0099955 | 0.0099962 | 0.0099968 | 0.0099973 | 0.0099977 | 0.009998 | 0.0099983 | 0.0099986 | 0.0099988 | 0.009999 | 0.0099991 | 0.0099993 | 0.0099994 | 0.0099995 | 0.0099995 | 0.0099996 | 0.0099997 | 0.0099997 | 0.0099998 | 0.0099998 | 0.0099998 | 0.0099999 | 0.0099999 | 0.0099999 | 0.0099999 | 0.0099999 | 0.0099999 | 0.0099999 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01
| 1 | 39.0338 | 0.0022572 | 0.0027087 | 0.0031911 | 0.0036971 | 0.0042196 | 0.004751 | 0.0052841 | 0.0058124 | 0.00633 | 0.0068316 | 0.0073133 | 0.0077715 | 0.0082039 | 0.0086089 | 0.0089854 | 0.0093333 | 0.0096528 | 0.0099445 | 0.010209 | 0.010449 | 0.010665 | 0.010858 | 0.01103 | 0.011184 | 0.01132 | 0.01144 | 0.011546 | 0.011639 | 0.01172 | 0.011792 | 0.011854 | 0.011908 | 0.011955 | 0.011996 | 0.012032 | 0.012062 | 0.012089 | 0.012111 | 0.012131 | 0.012148 | 0.012162 | 0.012175 | 0.012186 | 0.012195 | 0.012203 | 0.012209 | 0.012215 | 0.01222 | 0.012224 | 0.012228 | 0.012231 | 0.012233 | 0.012236 | 0.012237 | 0.012239 | 0.01224 | 0.012242 | 0.012243 | 0.012243 | 0.012244 | 0.012245 | 0.012245 | 0.012246 | 0.012246 | 0.012246 | 0.012247 | 0.012247 | 0.012247 | 0.012247 | 0.012247 | 0.012248 | 0.012248 | 0.012248 | 0.012248 | 0.012248 | 0.012248 | 0.012248 | 0.012248 | 0.012248 | 0.012248 | 0.012248 | 0.012248 | 0.012248 | 0.012248 | 0.012248 | 0.012248 | 0.012248 | 0.012248 | 0.012248 | 0.012248 | 0.012248 | 0.012248 | 0.012248 | 0.012248 | 0.012248 | 0.012248 | 0.012248 | 0.012248 | 0.012248 | 0.012248 | 0.012248
| 2 | 40.1761 | 0.0025428 | 0.003066 | 0.0036284 | 0.0042222 | 0.0048389 | 0.0054698 | 0.0061064 | 0.0067408 | 0.0073658 | 0.0079748 | 0.0085626 | 0.0091248 | 0.0096579 | 0.01016 | 0.010629 | 0.011064 | 0.011465 | 0.011834 | 0.01217 | 0.012475 | 0.012751 | 0.012999 | 0.013222 | 0.013421 | 0.013597 | 0.013754 | 0.013893 | 0.014016 | 0.014124 | 0.014218 | 0.014301 | 0.014373 | 0.014437 | 0.014492 | 0.014539 | 0.014581 | 0.014617 | 0.014648 | 0.014675 | 0.014698 | 0.014718 | 0.014735 | 0.01475 | 0.014762 | 0.014773 | 0.014783 | 0.014791 | 0.014798 | 0.014804 | 0.014809 | 0.014813 | 0.014817 | 0.01482 | 0.014823 | 0.014825 | 0.014827 | 0.014828 | 0.01483 | 0.014831 | 0.014832 | 0.014833 | 0.014834 | 0.014834 | 0.014835 | 0.014836 | 0.014836 | 0.014836 | 0.014837 | 0.014837 | 0.014837 | 0.014837 | 0.014837 | 0.014837 | 0.014838 | 0.014838 | 0.014838 | 0.014838 | 0.014838 | 0.014838 | 0.014838 | 0.014838 | 0.014838 | 0.014838 | 0.014838 | 0.014838 | 0.014838 | 0.014838 | 0.014838 | 0.014838 | 0.014838 | 0.014838 | 0.014838 | 0.014838 | 0.014838 | 0.014838 | 0.014838 | 0.014838 | 0.014838 | 0.014838 | 0.014838 | 0.014838
| 3 | 41.3184 | 0.0028378 | 0.0034374 | 0.0040858 | 0.0047745 | 0.0054938 | 0.0062339 | 0.006985 | 0.0077374 | 0.0084825 | 0.0092125 | 0.0099206 | 0.010601 | 0.01125 | 0.011863 | 0.012439 | 0.012976 | 0.013474 | 0.013932 | 0.014353 | 0.014736 | 0.015084 | 0.015398 | 0.015681 | 0.015935 | 0.016161 | 0.016363 | 0.016543 | 0.016701 | 0.016841 | 0.016965 | 0.017073 | 0.017169 | 0.017252 | 0.017325 | 0.017388 | 0.017443 | 0.017491 | 0.017533 | 0.017569 | 0.0176 | 0.017627 | 0.017651 | 0.017671 | 0.017688 | 0.017703 | 0.017716 | 0.017727 | 0.017737 | 0.017745 | 0.017752 | 0.017758 | 0.017763 | 0.017768 | 0.017771 | 0.017775 | 0.017777 | 0.01778 | 0.017782 | 0.017783 | 0.017785 | 0.017786 | 0.017787 | 0.017788 | 0.017789 | 0.01779 | 0.01779 | 0.017791 | 0.017791 | 0.017792 | 0.017792 | 0.017792 | 0.017792 | 0.017793 | 0.017793 | 0.017793 | 0.017793 | 0.017793 | 0.017793 | 0.017793 | 0.017793 | 0.017793 | 0.017793 | 0.017794 | 0.017794 | 0.017794 | 0.017794 | 0.017794 | 0.017794 | 0.017794 | 0.017794 | 0.017794 | 0.017794 | 0.017794 | 0.017794 | 0.017794 | 0.017794 | 0.017794 | 0.017794 | 0.017794 | 0.017794 | 0.017794
| 4 | 42.4607 | 0.0031398 | 0.00382 | 0.0045599 | 0.0053501 | 0.0061801 | 0.0070388 | 0.0079148 | 0.008797 | 0.0096751 | 0.01054 | 0.011382 | 0.012196 | 0.012976 | 0.013716 | 0.014414 | 0.015069 | 0.015677 | 0.016241 | 0.016759 | 0.017234 | 0.017667 | 0.018059 | 0.018414 | 0.018733 | 0.01902 | 0.019276 | 0.019504 | 0.019707 | 0.019886 | 0.020045 | 0.020185 | 0.020309 | 0.020417 | 0.020512 | 0.020595 | 0.020667 | 0.02073 | 0.020785 | 0.020833 | 0.020875 | 0.020911 | 0.020942 | 0.020969 | 0.020992 | 0.021012 | 0.02103 | 0.021045 | 0.021058 | 0.021069 | 0.021078 | 0.021087 | 0.021094 | 0.0211 | 0.021105 | 0.02111 | 0.021113 | 0.021117 | 0.02112 | 0.021122 | 0.021124 | 0.021126 | 0.021127 | 0.021129 | 0.02113 | 0.021131 | 0.021132 | 0.021132 | 0.021133 | 0.021133 | 0.021134 | 0.021134 | 0.021135 | 0.021135 | 0.021135 | 0.021135 | 0.021135 | 0.021136 | 0.021136 | 0.021136 | 0.021136 | 0.021136 | 0.021136 | 0.021136 | 0.021136 | 0.021136 | 0.021136 | 0.021136 | 0.021136 | 0.021136 | 0.021136 | 0.021136 | 0.021136 | 0.021136 | 0.021136 | 0.021136 | 0.021136 | 0.021137 | 0.021137 | 0.021137 | 0.021137 | 0.021137
| 5 | 43.603 | 0.0034464 | 0.0042109 | 0.0050471 | 0.005945 | 0.0068933 | 0.0078793 | 0.0088904 | 0.0099139 | 0.010938 | 0.01195 | 0.012942 | 0.013905 | 0.01483 | 0.015714 | 0.016551 | 0.017338 | 0.018074 | 0.018757 | 0.019389 | 0.01997 | 0.020501 | 0.020985 | 0.021424 | 0.021821 | 0.022178 | 0.022499 | 0.022785 | 0.023041 | 0.023268 | 0.023469 | 0.023648 | 0.023805 | 0.023944 | 0.024066 | 0.024173 | 0.024266 | 0.024348 | 0.02442 | 0.024482 | 0.024537 | 0.024584 | 0.024625 | 0.024661 | 0.024692 | 0.024718 | 0.024742 | 0.024762 | 0.024779 | 0.024794 | 0.024807 | 0.024818 | 0.024827 | 0.024836 | 0.024843 | 0.024849 | 0.024854 | 0.024859 | 0.024863 | 0.024866 | 0.024869 | 0.024871 | 0.024873 | 0.024875 | 0.024877 | 0.024878 | 0.024879 | 0.02488 | 0.024881 | 0.024882 | 0.024882 | 0.024883 | 0.024883 | 0.024884 | 0.024884 | 0.024885 | 0.024885 | 0.024885 | 0.024885 | 0.024885 | 0.024885 | 0.024886 | 0.024886 | 0.024886 | 0.024886 | 0.024886 | 0.024886 | 0.024886 | 0.024886 | 0.024886 | 0.024886 | 0.024886 | 0.024886 | 0.024886 | 0.024886 | 0.024886 | 0.024886 | 0.024886 | 0.024886 | 0.024886 | 0.024886 | 0.024886
Cost ($) | 6 | 44.7453 | 0.0037556 | 0.0046074 | 0.005544 | 0.0065551 | 0.0076283 | 0.00875 | 0.0099058 | 0.011081 | 0.012263 | 0.013437 | 0.014593 | 0.015719 | 0.016807 | 0.017849 | 0.018841 | 0.019778 | 0.020657 | 0.021478 | 0.022239 | 0.022941 | 0.023586 | 0.024176 | 0.024713 | 0.0252 | 0.025639 | 0.026035 | 0.026391 | 0.026709 | 0.026992 | 0.027245 | 0.027469 | 0.027667 | 0.027843 | 0.027997 | 0.028133 | 0.028253 | 0.028358 | 0.02845 | 0.02853 | 0.0286 | 0.028662 | 0.028715 | 0.028761 | 0.028802 | 0.028837 | 0.028867 | 0.028893 | 0.028916 | 0.028936 | 0.028953 | 0.028968 | 0.028981 | 0.028992 | 0.029001 | 0.029009 | 0.029016 | 0.029023 | 0.029028 | 0.029032 | 0.029036 | 0.02904 | 0.029042 | 0.029045 | 0.029047 | 0.029049 | 0.029051 | 0.029052 | 0.029053 | 0.029054 | 0.029055 | 0.029056 | 0.029056 | 0.029057 | 0.029057 | 0.029058 | 0.029058 | 0.029058 | 0.029059 | 0.029059 | 0.029059 | 0.029059 | 0.029059 | 0.02906 | 0.02906 | 0.02906 | 0.02906 | 0.02906 | 0.02906 | 0.02906 | 0.02906 | 0.02906 | 0.02906 | 0.02906 | 0.02906 | 0.02906 | 0.02906 | 0.02906 | 0.02906 | 0.02906 | 0.02906 | 0.02906
| 7 | 45.8876 | 0.004065 | 0.0050065 | 0.0060472 | 0.0071762 | 0.0083805 | 0.0096452 | 0.010955 | 0.012293 | 0.013644 | 0.014992 | 0.016325 | 0.01763 | 0.018896 | 0.020114 | 0.021278 | 0.022381 | 0.023421 | 0.024395 | 0.025302 | 0.026142 | 0.026917 | 0.027627 | 0.028276 | 0.028867 | 0.029403 | 0.029886 | 0.030322 | 0.030713 | 0.031063 | 0.031375 | 0.031654 | 0.031901 | 0.03212 | 0.032314 | 0.032485 | 0.032635 | 0.032768 | 0.032884 | 0.032987 | 0.033076 | 0.033154 | 0.033223 | 0.033282 | 0.033334 | 0.033379 | 0.033419 | 0.033453 | 0.033483 | 0.033508 | 0.033531 | 0.03355 | 0.033567 | 0.033581 | 0.033594 | 0.033605 | 0.033614 | 0.033622 | 0.033629 | 0.033635 | 0.033641 | 0.033645 | 0.033649 | 0.033652 | 0.033655 | 0.033658 | 0.03366 | 0.033662 | 0.033663 | 0.033665 | 0.033666 | 0.033667 | 0.033668 | 0.033669 | 0.033669 | 0.03367 | 0.03367 | 0.033671 | 0.033671 | 0.033671 | 0.033672 | 0.033672 | 0.033672 | 0.033672 | 0.033672 | 0.033673 | 0.033673 | 0.033673 | 0.033673 | 0.033673 | 0.033673 | 0.033673 | 0.033673 | 0.033673 | 0.033673 | 0.033673 | 0.033673 | 0.033673 | 0.033673 | 0.033673 | 0.033673 | 0.033673
| 8 | 47.0299 | 0.0043727 | 0.0054059 | 0.0065533 | 0.0078042 | 0.0091448 | 0.010559 | 0.012031 | 0.013541 | 0.015072 | 0.016608 | 0.018132 | 0.019629 | 0.021089 | 0.022499 | 0.023851 | 0.025138 | 0.026356 | 0.027501 | 0.028571 | 0.029566 | 0.030486 | 0.031333 | 0.03211 | 0.032819 | 0.033464 | 0.034049 | 0.034577 | 0.035053 | 0.03548 | 0.035862 | 0.036204 | 0.036508 | 0.036779 | 0.037019 | 0.037231 | 0.037419 | 0.037585 | 0.03773 | 0.037859 | 0.037971 | 0.03807 | 0.038157 | 0.038232 | 0.038298 | 0.038356 | 0.038406 | 0.03845 | 0.038488 | 0.038522 | 0.03855 | 0.038576 | 0.038597 | 0.038616 | 0.038633 | 0.038647 | 0.038659 | 0.03867 | 0.038679 | 0.038687 | 0.038694 | 0.0387 | 0.038705 | 0.038709 | 0.038713 | 0.038716 | 0.038719 | 0.038722 | 0.038724 | 0.038726 | 0.038727 | 0.038729 | 0.03873 | 0.038731 | 0.038732 | 0.038733 | 0.038733 | 0.038734 | 0.038734 | 0.038735 | 0.038735 | 0.038735 | 0.038736 | 0.038736 | 0.038736 | 0.038736 | 0.038736 | 0.038737 | 0.038737 | 0.038737 | 0.038737 | 0.038737 | 0.038737 | 0.038737 | 0.038737 | 0.038737 | 0.038737 | 0.038737 | 0.038737 | 0.038737 | 0.038737 | 0.038737
| 9 | 48.1722 | 0.004677 | 0.0058029 | 0.0070592 | 0.0084352 | 0.0099166 | 0.011487 | 0.013127 | 0.014818 | 0.01654 | 0.018274 | 0.020001 | 0.021707 | 0.023375 | 0.024992 | 0.02655 | 0.028038 | 0.029451 | 0.030784 | 0.032035 | 0.033201 | 0.034284 | 0.035285 | 0.036205 | 0.037049 | 0.037818 | 0.038517 | 0.039151 | 0.039724 | 0.04024 | 0.040703 | 0.041118 | 0.041489 | 0.041819 | 0.042113 | 0.042374 | 0.042606 | 0.04281 | 0.042991 | 0.04315 | 0.04329 | 0.043414 | 0.043522 | 0.043617 | 0.0437 | 0.043773 | 0.043837 | 0.043892 | 0.043941 | 0.043983 | 0.04402 | 0.044052 | 0.04408 | 0.044104 | 0.044125 | 0.044143 | 0.044159 | 0.044173 | 0.044185 | 0.044195 | 0.044204 | 0.044212 | 0.044219 | 0.044225 | 0.04423 | 0.044234 | 0.044238 | 0.044241 | 0.044244 | 0.044246 | 0.044248 | 0.04425 | 0.044252 | 0.044253 | 0.044254 | 0.044255 | 0.044256 | 0.044257 | 0.044258 | 0.044258 | 0.044259 | 0.044259 | 0.04426 | 0.04426 | 0.04426 | 0.04426 | 0.044261 | 0.044261 | 0.044261 | 0.044261 | 0.044261 | 0.044261 | 0.044261 | 0.044261 | 0.044262 | 0.044262 | 0.044262 | 0.044262 | 0.044262 | 0.044262 | 0.044262 | 0.044262
| 10 | 49.3146 | 0.0049761 | 0.0061954 | 0.0075621 | 0.0090656 | 0.010691 | 0.012422 | 0.014237 | 0.016117 | 0.018039 | 0.019981 | 0.021925 | 0.023851 | 0.025742 | 0.027583 | 0.029362 | 0.031068 | 0.032694 | 0.034233 | 0.035682 | 0.037038 | 0.038301 | 0.039472 | 0.040553 | 0.041546 | 0.042455 | 0.043284 | 0.044037 | 0.04472 | 0.045337 | 0.045892 | 0.046391 | 0.046838 | 0.047238 | 0.047595 | 0.047912 | 0.048194 | 0.048445 | 0.048666 | 0.048862 | 0.049035 | 0.049187 | 0.049321 | 0.049439 | 0.049542 | 0.049633 | 0.049713 | 0.049782 | 0.049843 | 0.049896 | 0.049943 | 0.049983 | 0.050019 | 0.050049 | 0.050076 | 0.0501 | 0.05012 | 0.050138 | 0.050153 | 0.050166 | 0.050178 | 0.050188 | 0.050197 | 0.050204 | 0.050211 | 0.050216 | 0.050221 | 0.050226 | 0.050229 | 0.050232 | 0.050235 | 0.050238 | 0.05024 | 0.050242 | 0.050243 | 0.050244 | 0.050246 | 0.050247 | 0.050248 | 0.050248 | 0.050249 | 0.05025 | 0.05025 | 0.05025 | 0.050251 | 0.050251 | 0.050251 | 0.050252 | 0.050252 | 0.050252 | 0.050252 | 0.050252 | 0.050252 | 0.050253 | 0.050253 | 0.050253 | 0.050253 | 0.050253 | 0.050253 | 0.050253 | 0.050253 | 0.050253
| 11 | 50.4569 | 0.0052687 | 0.0065814 | 0.0080592 | 0.0096918 | 0.011465 | 0.01336 | 0.015356 | 0.01743 | 0.01956 | 0.021722 | 0.023893 | 0.026052 | 0.028179 | 0.030259 | 0.032275 | 0.034215 | 0.036071 | 0.037833 | 0.039498 | 0.041061 | 0.042522 | 0.043881 | 0.045138 | 0.046298 | 0.047362 | 0.048336 | 0.049224 | 0.050031 | 0.050762 | 0.051422 | 0.052016 | 0.052551 | 0.05303 | 0.053458 | 0.053841 | 0.054181 | 0.054484 | 0.054753 | 0.054991 | 0.055202 | 0.055388 | 0.055553 | 0.055697 | 0.055825 | 0.055937 | 0.056035 | 0.056122 | 0.056197 | 0.056263 | 0.056321 | 0.056372 | 0.056416 | 0.056455 | 0.056489 | 0.056518 | 0.056544 | 0.056566 | 0.056586 | 0.056603 | 0.056617 | 0.05663 | 0.056641 | 0.056651 | 0.05666 | 0.056667 | 0.056673 | 0.056679 | 0.056683 | 0.056688 | 0.056691 | 0.056694 | 0.056697 | 0.056699 | 0.056702 | 0.056703 | 0.056705 | 0.056706 | 0.056707 | 0.056708 | 0.056709 | 0.05671 | 0.056711 | 0.056711 | 0.056712 | 0.056712 | 0.056712 | 0.056713 | 0.056713 | 0.056713 | 0.056714 | 0.056714 | 0.056714 | 0.056714 | 0.056714 | 0.056714 | 0.056714 | 0.056714 | 0.056714 | 0.056715 | 0.056715 | 0.056715
| 12 | 51.5992 | 0.0055534 | 0.0069591 | 0.0085481 | 0.010311 | 0.012233 | 0.014295 | 0.016476 | 0.018751 | 0.021096 | 0.023486 | 0.025894 | 0.028297 | 0.030674 | 0.033006 | 0.035274 | 0.037465 | 0.039567 | 0.04157 | 0.043468 | 0.045256 | 0.046933 | 0.048497 | 0.049949 | 0.051291 | 0.052528 | 0.053662 | 0.054699 | 0.055644 | 0.056503 | 0.05728 | 0.057983 | 0.058616 | 0.059184 | 0.059695 | 0.060151 | 0.060559 | 0.060922 | 0.061245 | 0.061533 | 0.061787 | 0.062013 | 0.062212 | 0.062389 | 0.062544 | 0.062681 | 0.062802 | 0.062908 | 0.063001 | 0.063082 | 0.063154 | 0.063217 | 0.063272 | 0.06332 | 0.063362 | 0.063399 | 0.063431 | 0.063459 | 0.063483 | 0.063505 | 0.063523 | 0.063539 | 0.063553 | 0.063566 | 0.063576 | 0.063586 | 0.063594 | 0.063601 | 0.063607 | 0.063612 | 0.063617 | 0.063621 | 0.063625 | 0.063628 | 0.06363 | 0.063633 | 0.063635 | 0.063636 | 0.063638 | 0.063639 | 0.06364 | 0.063641 | 0.063642 | 0.063643 | 0.063643 | 0.063644 | 0.063645 | 0.063645 | 0.063645 | 0.063646 | 0.063646 | 0.063646 | 0.063646 | 0.063647 | 0.063647 | 0.063647 | 0.063647 | 0.063647 | 0.063647 | 0.063647 | 0.063647 | 0.063647
| 13 | 52.7415 | 0.0058293 | 0.007327 | 0.0090267 | 0.01092 | 0.012991 | 0.015223 | 0.017592 | 0.020074 | 0.02264 | 0.025264 | 0.027918 | 0.030577 | 0.033215 | 0.035812 | 0.038347 | 0.040803 | 0.043167 | 0.045427 | 0.047576 | 0.049607 | 0.051516 | 0.053303 | 0.054966 | 0.056509 | 0.057934 | 0.059245 | 0.060447 | 0.061546 | 0.062546 | 0.063455 | 0.064278 | 0.065021 | 0.065691 | 0.066293 | 0.066833 | 0.067317 | 0.067749 | 0.068135 | 0.068478 | 0.068783 | 0.069054 | 0.069294 | 0.069506 | 0.069694 | 0.06986 | 0.070006 | 0.070135 | 0.070249 | 0.070349 | 0.070436 | 0.070513 | 0.070581 | 0.07064 | 0.070692 | 0.070737 | 0.070777 | 0.070812 | 0.070842 | 0.070869 | 0.070892 | 0.070912 | 0.07093 | 0.070946 | 0.070959 | 0.070971 | 0.070981 | 0.07099 | 0.070998 | 0.071004 | 0.07101 | 0.071015 | 0.07102 | 0.071024 | 0.071027 | 0.07103 | 0.071033 | 0.071035 | 0.071037 | 0.071038 | 0.07104 | 0.071041 | 0.071042 | 0.071043 | 0.071044 | 0.071045 | 0.071045 | 0.071046 | 0.071047 | 0.071047 | 0.071047 | 0.071048 | 0.071048 | 0.071048 | 0.071048 | 0.071049 | 0.071049 | 0.071049 | 0.071049 | 0.071049 | 0.071049 | 0.071049
| 14 | 53.8838 | 0.0060955 | 0.0076838 | 0.0094932 | 0.011516 | 0.013738 | 0.01614 | 0.0187 | 0.02139 | 0.024183 | 0.027048 | 0.029956 | 0.032879 | 0.03579 | 0.038664 | 0.041478 | 0.044214 | 0.046856 | 0.04939 | 0.051805 | 0.054095 | 0.056255 | 0.058282 | 0.060174 | 0.061934 | 0.063565 | 0.065069 | 0.066451 | 0.067718 | 0.068875 | 0.069929 | 0.070885 | 0.071752 | 0.072534 | 0.073239 | 0.073874 | 0.074443 | 0.074953 | 0.075409 | 0.075815 | 0.076178 | 0.0765 | 0.076787 | 0.077041 | 0.077266 | 0.077465 | 0.077641 | 0.077797 | 0.077934 | 0.078055 | 0.078161 | 0.078255 | 0.078337 | 0.078409 | 0.078473 | 0.078528 | 0.078577 | 0.07862 | 0.078657 | 0.07869 | 0.078719 | 0.078744 | 0.078766 | 0.078785 | 0.078802 | 0.078816 | 0.078829 | 0.07884 | 0.07885 | 0.078859 | 0.078866 | 0.078872 | 0.078878 | 0.078883 | 0.078887 | 0.078891 | 0.078894 | 0.078897 | 0.0789 | 0.078902 | 0.078904 | 0.078905 | 0.078907 | 0.078908 | 0.078909 | 0.07891 | 0.078911 | 0.078911 | 0.078912 | 0.078913 | 0.078913 | 0.078914 | 0.078914 | 0.078914 | 0.078914 | 0.078915 | 0.078915 | 0.078915 | 0.078915 | 0.078915 | 0.078916 | 0.078916
| 15 | 55.0261 | 0.0063514 | 0.0080285 | 0.0099461 | 0.012097 | 0.014469 | 0.017043 | 0.019794 | 0.022696 | 0.025718 | 0.02883 | 0.031999 | 0.035194 | 0.038386 | 0.041548 | 0.044654 | 0.047684 | 0.050617 | 0.053439 | 0.056138 | 0.058704 | 0.061131 | 0.063414 | 0.065553 | 0.067548 | 0.0694 | 0.071113 | 0.072693 | 0.074143 | 0.075472 | 0.076685 | 0.077788 | 0.078791 | 0.079698 | 0.080518 | 0.081257 | 0.081922 | 0.082518 | 0.083053 | 0.083531 | 0.083958 | 0.084339 | 0.084678 | 0.08498 | 0.085247 | 0.085485 | 0.085695 | 0.085881 | 0.086045 | 0.08619 | 0.086318 | 0.086431 | 0.086531 | 0.086618 | 0.086695 | 0.086763 | 0.086822 | 0.086874 | 0.08692 | 0.08696 | 0.086995 | 0.087026 | 0.087053 | 0.087077 | 0.087097 | 0.087115 | 0.087131 | 0.087145 | 0.087157 | 0.087168 | 0.087177 | 0.087185 | 0.087192 | 0.087198 | 0.087203 | 0.087208 | 0.087212 | 0.087216 | 0.087219 | 0.087222 | 0.087224 | 0.087226 | 0.087228 | 0.08723 | 0.087231 | 0.087232 | 0.087233 | 0.087234 | 0.087235 | 0.087236 | 0.087236 | 0.087237 | 0.087237 | 0.087238 | 0.087238 | 0.087238 | 0.087238 | 0.087239 | 0.087239 | 0.087239 | 0.087239 | 0.087239
| 16 | 56.1684 | 0.0065964 | 0.0083602 | 0.010384 | 0.012662 | 0.015183 | 0.017927 | 0.02087 | 0.023985 | 0.02724 | 0.030602 | 0.034037 | 0.037511 | 0.040993 | 0.044453 | 0.047862 | 0.051197 | 0.054435 | 0.05756 | 0.060557 | 0.063414 | 0.066124 | 0.068682 | 0.071083 | 0.073329 | 0.07542 | 0.077359 | 0.079151 | 0.080801 | 0.082316 | 0.083703 | 0.084968 | 0.086119 | 0.087164 | 0.08811 | 0.088965 | 0.089736 | 0.090429 | 0.091052 | 0.09161 | 0.09211 | 0.092556 | 0.092954 | 0.093309 | 0.093625 | 0.093905 | 0.094154 | 0.094375 | 0.09457 | 0.094743 | 0.094896 | 0.095031 | 0.09515 | 0.095255 | 0.095348 | 0.095429 | 0.095501 | 0.095564 | 0.095619 | 0.095668 | 0.095711 | 0.095748 | 0.095781 | 0.09581 | 0.095835 | 0.095857 | 0.095877 | 0.095894 | 0.095909 | 0.095922 | 0.095933 | 0.095943 | 0.095952 | 0.095959 | 0.095966 | 0.095972 | 0.095977 | 0.095981 | 0.095985 | 0.095989 | 0.095992 | 0.095994 | 0.095997 | 0.095999 | 0.096 | 0.096002 | 0.096003 | 0.096004 | 0.096005 | 0.096006 | 0.096007 | 0.096008 | 0.096008 | 0.096009 | 0.096009 | 0.09601 | 0.09601 | 0.09601 | 0.09601 | 0.096011 | 0.096011 | 0.096011
| 17 | 57.3107 | 0.0068302 | 0.0086783 | 0.010806 | 0.013209 | 0.015876 | 0.018789 | 0.021924 | 0.025253 | 0.028742 | 0.032357 | 0.036062 | 0.039822 | 0.0436 | 0.047366 | 0.051088 | 0.054738 | 0.058294 | 0.061735 | 0.065044 | 0.068208 | 0.071217 | 0.074064 | 0.076744 | 0.079257 | 0.081603 | 0.083784 | 0.085805 | 0.08767 | 0.089387 | 0.090961 | 0.092402 | 0.093715 | 0.094911 | 0.095995 | 0.096978 | 0.097865 | 0.098666 | 0.099386 | 0.10003 | 0.10061 | 0.10113 | 0.1016 | 0.10201 | 0.10238 | 0.10271 | 0.103 | 0.10326 | 0.10349 | 0.1037 | 0.10388 | 0.10404 | 0.10418 | 0.10431 | 0.10442 | 0.10451 | 0.1046 | 0.10468 | 0.10474 | 0.1048 | 0.10485 | 0.1049 | 0.10494 | 0.10497 | 0.105 | 0.10503 | 0.10505 | 0.10507 | 0.10509 | 0.10511 | 0.10512 | 0.10513 | 0.10515 | 0.10515 | 0.10516 | 0.10517 | 0.10518 | 0.10518 | 0.10519 | 0.10519 | 0.10519 | 0.1052 | 0.1052 | 0.1052 | 0.10521 | 0.10521 | 0.10521 | 0.10521 | 0.10521 | 0.10521 | 0.10521 | 0.10521 | 0.10522 | 0.10522 | 0.10522 | 0.10522 | 0.10522 | 0.10522 | 0.10522 | 0.10522 | 0.10522 | 0.10522
| 18 | 58.453 | 0.0070525 | 0.0089823 | 0.011211 | 0.013736 | 0.016547 | 0.019628 | 0.022954 | 0.026495 | 0.030219 | 0.034089 | 0.038067 | 0.042115 | 0.046197 | 0.050275 | 0.054318 | 0.058295 | 0.062179 | 0.065948 | 0.069583 | 0.073067 | 0.076389 | 0.07954 | 0.082515 | 0.085311 | 0.087928 | 0.090367 | 0.092632 | 0.094728 | 0.096661 | 0.098439 | 0.10007 | 0.10156 | 0.10292 | 0.10415 | 0.10527 | 0.10629 | 0.10721 | 0.10803 | 0.10878 | 0.10945 | 0.11005 | 0.11059 | 0.11107 | 0.1115 | 0.11188 | 0.11222 | 0.11253 | 0.1128 | 0.11304 | 0.11325 | 0.11344 | 0.11361 | 0.11376 | 0.11389 | 0.114 | 0.1141 | 0.11419 | 0.11427 | 0.11434 | 0.1144 | 0.11446 | 0.11451 | 0.11455 | 0.11459 | 0.11462 | 0.11465 | 0.11467 | 0.11469 | 0.11471 | 0.11473 | 0.11475 | 0.11476 | 0.11477 | 0.11478 | 0.11479 | 0.1148 | 0.1148 | 0.11481 | 0.11481 | 0.11482 | 0.11482 | 0.11483 | 0.11483 | 0.11483 | 0.11483 | 0.11484 | 0.11484 | 0.11484 | 0.11484 | 0.11484 | 0.11484 | 0.11484 | 0.11485 | 0.11485 | 0.11485 | 0.11485 | 0.11485 | 0.11485 | 0.11485 | 0.11485 | 0.11485
| 19 | 59.5953 | 0.0072634 | 0.009272 | 0.011599 | 0.014243 | 0.017196 | 0.020441 | 0.023955 | 0.027708 | 0.031666 | 0.035792 | 0.040045 | 0.044385 | 0.048773 | 0.053171 | 0.057541 | 0.061853 | 0.066075 | 0.070183 | 0.074155 | 0.077972 | 0.081621 | 0.085092 | 0.088376 | 0.09147 | 0.094373 | 0.097085 | 0.09961 | 0.10195 | 0.10412 | 0.10611 | 0.10795 | 0.10963 | 0.11116 | 0.11256 | 0.11383 | 0.11499 | 0.11603 | 0.11698 | 0.11783 | 0.1186 | 0.11929 | 0.11991 | 0.12046 | 0.12096 | 0.1214 | 0.1218 | 0.12215 | 0.12247 | 0.12275 | 0.12299 | 0.12322 | 0.12341 | 0.12358 | 0.12374 | 0.12387 | 0.124 | 0.1241 | 0.1242 | 0.12428 | 0.12435 | 0.12442 | 0.12447 | 0.12452 | 0.12457 | 0.12461 | 0.12464 | 0.12467 | 0.1247 | 0.12472 | 0.12474 | 0.12476 | 0.12478 | 0.12479 | 0.1248 | 0.12481 | 0.12482 | 0.12483 | 0.12484 | 0.12484 | 0.12485 | 0.12485 | 0.12486 | 0.12486 | 0.12487 | 0.12487 | 0.12487 | 0.12487 | 0.12487 | 0.12488 | 0.12488 | 0.12488 | 0.12488 | 0.12488 | 0.12488 | 0.12488 | 0.12488 | 0.12488 | 0.12489 | 0.12489 | 0.12489 | 0.12489
| 20 | 60.7376 | 0.0074629 | 0.0095472 | 0.011969 | 0.014728 | 0.01782 | 0.021227 | 0.024926 | 0.028889 | 0.03308 | 0.03746 | 0.041988 | 0.046623 | 0.051321 | 0.056042 | 0.060746 | 0.065399 | 0.069968 | 0.074425 | 0.078745 | 0.082907 | 0.086896 | 0.090698 | 0.094306 | 0.097712 | 0.10092 | 0.10392 | 0.10672 | 0.10932 | 0.11173 | 0.11396 | 0.11601 | 0.11789 | 0.11962 | 0.12119 | 0.12263 | 0.12393 | 0.12512 | 0.12619 | 0.12716 | 0.12803 | 0.12882 | 0.12953 | 0.13016 | 0.13074 | 0.13125 | 0.1317 | 0.13211 | 0.13247 | 0.1328 | 0.13309 | 0.13334 | 0.13357 | 0.13378 | 0.13395 | 0.13411 | 0.13426 | 0.13438 | 0.13449 | 0.13459 | 0.13468 | 0.13475 | 0.13482 | 0.13488 | 0.13493 | 0.13498 | 0.13502 | 0.13505 | 0.13509 | 0.13511 | 0.13514 | 0.13516 | 0.13518 | 0.1352 | 0.13521 | 0.13522 | 0.13523 | 0.13524 | 0.13525 | 0.13526 | 0.13527 | 0.13527 | 0.13528 | 0.13528 | 0.13529 | 0.13529 | 0.13529 | 0.1353 | 0.1353 | 0.1353 | 0.1353 | 0.1353 | 0.13531 | 0.13531 | 0.13531 | 0.13531 | 0.13531 | 0.13531 | 0.13531 | 0.13531 | 0.13531 | 0.13531
| 21 | 61.8799 | 0.0076509 | 0.009808 | 0.012321 | 0.015193 | 0.018418 | 0.021983 | 0.025865 | 0.030034 | 0.034456 | 0.03909 | 0.043893 | 0.048822 | 0.053832 | 0.058879 | 0.063922 | 0.068923 | 0.073845 | 0.078659 | 0.083336 | 0.087854 | 0.092193 | 0.09634 | 0.10028 | 0.10402 | 0.10754 | 0.11084 | 0.11393 | 0.1168 | 0.11948 | 0.12195 | 0.12423 | 0.12633 | 0.12826 | 0.13002 | 0.13163 | 0.1331 | 0.13444 | 0.13565 | 0.13674 | 0.13773 | 0.13863 | 0.13943 | 0.14016 | 0.14081 | 0.14139 | 0.14192 | 0.14238 | 0.1428 | 0.14318 | 0.14351 | 0.14381 | 0.14407 | 0.1443 | 0.14451 | 0.1447 | 0.14486 | 0.14501 | 0.14514 | 0.14525 | 0.14535 | 0.14544 | 0.14552 | 0.14559 | 0.14566 | 0.14571 | 0.14576 | 0.1458 | 0.14584 | 0.14587 | 0.1459 | 0.14593 | 0.14595 | 0.14597 | 0.14599 | 0.146 | 0.14602 | 0.14603 | 0.14604 | 0.14605 | 0.14606 | 0.14606 | 0.14607 | 0.14607 | 0.14608 | 0.14608 | 0.14609 | 0.14609 | 0.14609 | 0.1461 | 0.1461 | 0.1461 | 0.1461 | 0.1461 | 0.14611 | 0.14611 | 0.14611 | 0.14611 | 0.14611 | 0.14611 | 0.14611 | 0.14611
| 22 | 63.0222 | 0.0078279 | 0.010054 | 0.012655 | 0.015635 | 0.018991 | 0.02271 | 0.02677 | 0.031142 | 0.035791 | 0.040676 | 0.045753 | 0.050976 | 0.056299 | 0.061674 | 0.067059 | 0.072411 | 0.077693 | 0.082871 | 0.087913 | 0.092796 | 0.097497 | 0.102 | 0.10629 | 0.11036 | 0.11421 | 0.11783 | 0.12122 | 0.12439 | 0.12733 | 0.13006 | 0.13259 | 0.13492 | 0.13706 | 0.13903 | 0.14083 | 0.14247 | 0.14396 | 0.14532 | 0.14656 | 0.14767 | 0.14868 | 0.14959 | 0.15042 | 0.15115 | 0.15182 | 0.15241 | 0.15295 | 0.15343 | 0.15385 | 0.15424 | 0.15458 | 0.15488 | 0.15515 | 0.15539 | 0.15561 | 0.1558 | 0.15597 | 0.15612 | 0.15625 | 0.15637 | 0.15647 | 0.15657 | 0.15665 | 0.15672 | 0.15678 | 0.15684 | 0.15689 | 0.15694 | 0.15697 | 0.15701 | 0.15704 | 0.15707 | 0.15709 | 0.15711 | 0.15713 | 0.15714 | 0.15716 | 0.15717 | 0.15718 | 0.15719 | 0.1572 | 0.15721 | 0.15722 | 0.15722 | 0.15723 | 0.15723 | 0.15724 | 0.15724 | 0.15724 | 0.15724 | 0.15725 | 0.15725 | 0.15725 | 0.15725 | 0.15725 | 0.15726 | 0.15726 | 0.15726 | 0.15726 | 0.15726 | 0.15726
| 23 | 64.1645 | 0.007994 | 0.010287 | 0.012971 | 0.016055 | 0.019537 | 0.023406 | 0.02764 | 0.032211 | 0.037084 | 0.042217 | 0.047565 | 0.053081 | 0.058715 | 0.06442 | 0.070148 | 0.075855 | 0.081501 | 0.087048 | 0.092464 | 0.097719 | 0.10279 | 0.10766 | 0.11231 | 0.11673 | 0.12092 | 0.12486 | 0.12857 | 0.13204 | 0.13527 | 0.13828 | 0.14106 | 0.14364 | 0.14601 | 0.14819 | 0.15018 | 0.15201 | 0.15368 | 0.1552 | 0.15658 | 0.15783 | 0.15896 | 0.15999 | 0.16091 | 0.16175 | 0.1625 | 0.16317 | 0.16378 | 0.16432 | 0.16481 | 0.16525 | 0.16563 | 0.16598 | 0.16629 | 0.16657 | 0.16682 | 0.16704 | 0.16723 | 0.1674 | 0.16756 | 0.16769 | 0.16782 | 0.16792 | 0.16802 | 0.1681 | 0.16818 | 0.16824 | 0.1683 | 0.16835 | 0.1684 | 0.16844 | 0.16848 | 0.16851 | 0.16854 | 0.16856 | 0.16858 | 0.1686 | 0.16862 | 0.16863 | 0.16865 | 0.16866 | 0.16867 | 0.16868 | 0.16869 | 0.16869 | 0.1687 | 0.1687 | 0.16871 | 0.16871 | 0.16872 | 0.16872 | 0.16872 | 0.16873 | 0.16873 | 0.16873 | 0.16873 | 0.16873 | 0.16873 | 0.16874 | 0.16874 | 0.16874 | 0.16874
| 24 | 65.3068 | 0.0081495 | 0.010505 | 0.01327 | 0.016454 | 0.020058 | 0.024071 | 0.028474 | 0.03324 | 0.038332 | 0.043709 | 0.049325 | 0.055131 | 0.061076 | 0.067109 | 0.073181 | 0.079246 | 0.085258 | 0.091179 | 0.096973 | 0.10261 | 0.10806 | 0.1133 | 0.11832 | 0.1231 | 0.12764 | 0.13193 | 0.13596 | 0.13974 | 0.14328 | 0.14657 | 0.14962 | 0.15245 | 0.15506 | 0.15747 | 0.15967 | 0.1617 | 0.16355 | 0.16524 | 0.16677 | 0.16817 | 0.16944 | 0.17059 | 0.17162 | 0.17256 | 0.17341 | 0.17417 | 0.17485 | 0.17547 | 0.17602 | 0.17651 | 0.17695 | 0.17735 | 0.1777 | 0.17802 | 0.1783 | 0.17855 | 0.17878 | 0.17898 | 0.17915 | 0.17931 | 0.17945 | 0.17957 | 0.17968 | 0.17978 | 0.17987 | 0.17995 | 0.18001 | 0.18007 | 0.18013 | 0.18018 | 0.18022 | 0.18025 | 0.18029 | 0.18032 | 0.18034 | 0.18036 | 0.18038 | 0.1804 | 0.18042 | 0.18043 | 0.18044 | 0.18045 | 0.18046 | 0.18047 | 0.18048 | 0.18049 | 0.18049 | 0.1805 | 0.1805 | 0.1805 | 0.18051 | 0.18051 | 0.18051 | 0.18052 | 0.18052 | 0.18052 | 0.18052 | 0.18052 | 0.18052 | 0.18053 | 0.18053
| 25 | 66.4491 | 0.0082948 | 0.01071 | 0.013552 | 0.016832 | 0.020552 | 0.024705 | 0.029272 | 0.034227 | 0.039534 | 0.04515 | 0.05103 | 0.057123 | 0.063375 | 0.069736 | 0.076152 | 0.082574 | 0.088955 | 0.095253 | 0.10143 | 0.10745 | 0.11328 | 0.11891 | 0.12431 | 0.12946 | 0.13436 | 0.13899 | 0.14337 | 0.14747 | 0.15132 | 0.15491 | 0.15825 | 0.16134 | 0.16421 | 0.16685 | 0.16928 | 0.17151 | 0.17355 | 0.17542 | 0.17712 | 0.17867 | 0.18008 | 0.18136 | 0.18252 | 0.18357 | 0.18452 | 0.18537 | 0.18614 | 0.18683 | 0.18745 | 0.18801 | 0.18851 | 0.18896 | 0.18936 | 0.18972 | 0.19004 | 0.19033 | 0.19058 | 0.19081 | 0.19101 | 0.19119 | 0.19135 | 0.19149 | 0.19162 | 0.19173 | 0.19183 | 0.19192 | 0.192 | 0.19207 | 0.19213 | 0.19219 | 0.19224 | 0.19228 | 0.19232 | 0.19235 | 0.19238 | 0.19241 | 0.19243 | 0.19245 | 0.19247 | 0.19249 | 0.1925 | 0.19251 | 0.19252 | 0.19253 | 0.19254 | 0.19255 | 0.19256 | 0.19256 | 0.19257 | 0.19257 | 0.19258 | 0.19258 | 0.19258 | 0.19259 | 0.19259 | 0.19259 | 0.19259 | 0.1926 | 0.1926 | 0.1926 | 0.1926
| 26 | 67.5914 | 0.0084304 | 0.010902 | 0.013817 | 0.017188 | 0.02102 | 0.025308 | 0.030034 | 0.035172 | 0.040688 | 0.046539 | 0.052678 | 0.059053 | 0.06561 | 0.072295 | 0.079053 | 0.085832 | 0.092583 | 0.09926 | 0.10582 | 0.11223 | 0.11846 | 0.12447 | 0.13025 | 0.13578 | 0.14105 | 0.14605 | 0.15077 | 0.15521 | 0.15938 | 0.16328 | 0.16691 | 0.17029 | 0.17341 | 0.1763 | 0.17897 | 0.18142 | 0.18366 | 0.18572 | 0.1876 | 0.18932 | 0.19088 | 0.1923 | 0.19358 | 0.19475 | 0.1958 | 0.19676 | 0.19762 | 0.19839 | 0.19909 | 0.19972 | 0.20028 | 0.20078 | 0.20124 | 0.20164 | 0.202 | 0.20233 | 0.20262 | 0.20288 | 0.20311 | 0.20331 | 0.2035 | 0.20366 | 0.2038 | 0.20393 | 0.20405 | 0.20415 | 0.20424 | 0.20432 | 0.20439 | 0.20446 | 0.20451 | 0.20456 | 0.20461 | 0.20465 | 0.20468 | 0.20471 | 0.20474 | 0.20476 | 0.20478 | 0.2048 | 0.20482 | 0.20483 | 0.20485 | 0.20486 | 0.20487 | 0.20488 | 0.20489 | 0.20489 | 0.2049 | 0.2049 | 0.20491 | 0.20491 | 0.20492 | 0.20492 | 0.20492 | 0.20493 | 0.20493 | 0.20493 | 0.20493 | 0.20493 | 0.20494
| 27 | 68.7337 | 0.0085566 | 0.011082 | 0.014065 | 0.017523 | 0.021463 | 0.02588 | 0.03076 | 0.036076 | 0.041794 | 0.047874 | 0.054267 | 0.060919 | 0.067777 | 0.074782 | 0.08188 | 0.089015 | 0.096135 | 0.10319 | 0.11014 | 0.11694 | 0.12356 | 0.12997 | 0.13614 | 0.14206 | 0.1477 | 0.15307 | 0.15815 | 0.16294 | 0.16744 | 0.17166 | 0.17559 | 0.17926 | 0.18266 | 0.18581 | 0.18871 | 0.19139 | 0.19386 | 0.19611 | 0.19818 | 0.20007 | 0.20179 | 0.20336 | 0.20478 | 0.20607 | 0.20724 | 0.2083 | 0.20926 | 0.21012 | 0.2109 | 0.2116 | 0.21223 | 0.2128 | 0.21331 | 0.21376 | 0.21417 | 0.21454 | 0.21486 | 0.21516 | 0.21542 | 0.21565 | 0.21586 | 0.21604 | 0.21621 | 0.21636 | 0.21649 | 0.2166 | 0.21671 | 0.2168 | 0.21688 | 0.21696 | 0.21702 | 0.21708 | 0.21713 | 0.21717 | 0.21721 | 0.21725 | 0.21728 | 0.21731 | 0.21733 | 0.21736 | 0.21737 | 0.21739 | 0.21741 | 0.21742 | 0.21743 | 0.21744 | 0.21745 | 0.21746 | 0.21747 | 0.21747 | 0.21748 | 0.21749 | 0.21749 | 0.21749 | 0.2175 | 0.2175 | 0.2175 | 0.21751 | 0.21751 | 0.21751 | 0.21751
| 28 | 69.876 | 0.0086739 | 0.01125 | 0.014298 | 0.017839 | 0.021881 | 0.026423 | 0.031449 | 0.036937 | 0.042853 | 0.049155 | 0.055795 | 0.06272 | 0.069872 | 0.077195 | 0.084628 | 0.092116 | 0.099603 | 0.10704 | 0.11437 | 0.12157 | 0.12859 | 0.13539 | 0.14196 | 0.14827 | 0.1543 | 0.16004 | 0.16549 | 0.17063 | 0.17547 | 0.18002 | 0.18427 | 0.18823 | 0.19192 | 0.19534 | 0.1985 | 0.20142 | 0.2041 | 0.20657 | 0.20883 | 0.2109 | 0.21279 | 0.21452 | 0.21609 | 0.21751 | 0.21881 | 0.21998 | 0.22104 | 0.222 | 0.22286 | 0.22364 | 0.22435 | 0.22498 | 0.22555 | 0.22606 | 0.22652 | 0.22693 | 0.22729 | 0.22762 | 0.22792 | 0.22818 | 0.22842 | 0.22863 | 0.22881 | 0.22898 | 0.22913 | 0.22926 | 0.22938 | 0.22949 | 0.22958 | 0.22966 | 0.22974 | 0.2298 | 0.22986 | 0.22991 | 0.22996 | 0.23 | 0.23004 | 0.23007 | 0.2301 | 0.23012 | 0.23014 | 0.23016 | 0.23018 | 0.2302 | 0.23021 | 0.23022 | 0.23023 | 0.23024 | 0.23025 | 0.23026 | 0.23027 | 0.23027 | 0.23028 | 0.23028 | 0.23029 | 0.23029 | 0.23029 | 0.2303 | 0.2303 | 0.2303 | 0.2303
| 29 | 71.0183 | 0.0087828 | 0.011406 | 0.014516 | 0.018136 | 0.022275 | 0.026935 | 0.032103 | 0.037756 | 0.043863 | 0.050381 | 0.057262 | 0.064453 | 0.071895 | 0.079529 | 0.087294 | 0.095131 | 0.10298 | 0.1108 | 0.11852 | 0.12611 | 0.13352 | 0.14073 | 0.14769 | 0.1544 | 0.16082 | 0.16694 | 0.17276 | 0.17827 | 0.18347 | 0.18835 | 0.19292 | 0.1972 | 0.20118 | 0.20487 | 0.2083 | 0.21147 | 0.21439 | 0.21707 | 0.21954 | 0.2218 | 0.22387 | 0.22576 | 0.22748 | 0.22905 | 0.23047 | 0.23176 | 0.23293 | 0.23399 | 0.23495 | 0.23582 | 0.2366 | 0.2373 | 0.23793 | 0.2385 | 0.23901 | 0.23947 | 0.23988 | 0.24025 | 0.24058 | 0.24088 | 0.24114 | 0.24138 | 0.24159 | 0.24178 | 0.24195 | 0.2421 | 0.24223 | 0.24235 | 0.24246 | 0.24255 | 0.24264 | 0.24271 | 0.24278 | 0.24284 | 0.24289 | 0.24294 | 0.24298 | 0.24301 | 0.24305 | 0.24308 | 0.2431 | 0.24313 | 0.24315 | 0.24316 | 0.24318 | 0.24319 | 0.24321 | 0.24322 | 0.24323 | 0.24324 | 0.24325 | 0.24325 | 0.24326 | 0.24326 | 0.24327 | 0.24327 | 0.24328 | 0.24328 | 0.24328 | 0.24329 | 0.24329
| 30 | 72.1606 | 0.0088837 | 0.011551 | 0.01472 | 0.018413 | 0.022646 | 0.027419 | 0.032722 | 0.038535 | 0.044825 | 0.051552 | 0.058668 | 0.066118 | 0.073843 | 0.081783 | 0.089874 | 0.098056 | 0.10627 | 0.11446 | 0.12257 | 0.13055 | 0.13836 | 0.14597 | 0.15334 | 0.16044 | 0.16726 | 0.17377 | 0.17997 | 0.18585 | 0.1914 | 0.19663 | 0.20153 | 0.20612 | 0.21041 | 0.21439 | 0.21809 | 0.22152 | 0.22468 | 0.22759 | 0.23027 | 0.23273 | 0.23499 | 0.23705 | 0.23893 | 0.24065 | 0.24221 | 0.24363 | 0.24491 | 0.24608 | 0.24714 | 0.24809 | 0.24895 | 0.24973 | 0.25043 | 0.25107 | 0.25163 | 0.25215 | 0.2526 | 0.25302 | 0.25339 | 0.25372 | 0.25401 | 0.25428 | 0.25452 | 0.25473 | 0.25492 | 0.25509 | 0.25524 | 0.25537 | 0.25549 | 0.2556 | 0.2557 | 0.25578 | 0.25586 | 0.25592 | 0.25598 | 0.25604 | 0.25608 | 0.25613 | 0.25616 | 0.2562 | 0.25623 | 0.25625 | 0.25628 | 0.2563 | 0.25632 | 0.25633 | 0.25635 | 0.25636 | 0.25637 | 0.25638 | 0.25639 | 0.2564 | 0.25641 | 0.25641 | 0.25642 | 0.25642 | 0.25643 | 0.25643 | 0.25644 | 0.25644 | 0.25644
| 31 | 73.3029 | 0.008977 | 0.011686 | 0.014909 | 0.018673 | 0.022994 | 0.027875 | 0.033307 | 0.039273 | 0.04574 | 0.05267 | 0.060013 | 0.067715 | 0.075716 | 0.083955 | 0.092366 | 0.10089 | 0.10946 | 0.11802 | 0.12651 | 0.13488 | 0.14309 | 0.1511 | 0.15887 | 0.16638 | 0.17359 | 0.1805 | 0.18708 | 0.19334 | 0.19925 | 0.20483 | 0.21008 | 0.215 | 0.21959 | 0.22387 | 0.22785 | 0.23154 | 0.23496 | 0.23811 | 0.24101 | 0.24368 | 0.24613 | 0.24837 | 0.25042 | 0.25229 | 0.25399 | 0.25555 | 0.25696 | 0.25824 | 0.2594 | 0.26045 | 0.2614 | 0.26226 | 0.26303 | 0.26373 | 0.26436 | 0.26493 | 0.26544 | 0.26589 | 0.2663 | 0.26667 | 0.267 | 0.2673 | 0.26757 | 0.2678 | 0.26802 | 0.26821 | 0.26838 | 0.26853 | 0.26866 | 0.26878 | 0.26889 | 0.26899 | 0.26907 | 0.26915 | 0.26922 | 0.26928 | 0.26933 | 0.26938 | 0.26942 | 0.26946 | 0.2695 | 0.26953 | 0.26955 | 0.26958 | 0.2696 | 0.26962 | 0.26963 | 0.26965 | 0.26966 | 0.26967 | 0.26968 | 0.26969 | 0.2697 | 0.26971 | 0.26971 | 0.26972 | 0.26973 | 0.26973 | 0.26973 | 0.26974 | 0.26974
| 32 | 74.4452 | 0.0090632 | 0.011811 | 0.015086 | 0.018916 | 0.02332 | 0.028303 | 0.03386 | 0.039971 | 0.046609 | 0.053733 | 0.061296 | 0.069243 | 0.077513 | 0.086044 | 0.094769 | 0.10362 | 0.11255 | 0.12147 | 0.13034 | 0.13911 | 0.14771 | 0.15612 | 0.1643 | 0.17221 | 0.17982 | 0.18712 | 0.1941 | 0.20073 | 0.20702 | 0.21296 | 0.21855 | 0.2238 | 0.22871 | 0.23329 | 0.23756 | 0.24153 | 0.2452 | 0.2486 | 0.25173 | 0.25461 | 0.25726 | 0.25969 | 0.26192 | 0.26395 | 0.26581 | 0.2675 | 0.26904 | 0.27044 | 0.27171 | 0.27286 | 0.2739 | 0.27485 | 0.2757 | 0.27647 | 0.27716 | 0.27779 | 0.27835 | 0.27886 | 0.27931 | 0.27972 | 0.28009 | 0.28042 | 0.28072 | 0.28098 | 0.28122 | 0.28143 | 0.28162 | 0.28179 | 0.28194 | 0.28208 | 0.2822 | 0.28231 | 0.2824 | 0.28249 | 0.28257 | 0.28264 | 0.2827 | 0.28275 | 0.2828 | 0.28284 | 0.28288 | 0.28292 | 0.28295 | 0.28297 | 0.283 | 0.28302 | 0.28304 | 0.28306 | 0.28307 | 0.28308 | 0.2831 | 0.28311 | 0.28312 | 0.28313 | 0.28313 | 0.28314 | 0.28315 | 0.28315 | 0.28316 | 0.28316 | 0.28316
| 33 | 75.5875 | 0.0091427 | 0.011927 | 0.01525 | 0.019143 | 0.023625 | 0.028706 | 0.03438 | 0.040632 | 0.047432 | 0.054744 | 0.062519 | 0.070703 | 0.079235 | 0.08805 | 0.097082 | 0.10626 | 0.11553 | 0.12482 | 0.13406 | 0.14321 | 0.15222 | 0.16103 | 0.1696 | 0.17791 | 0.18593 | 0.19363 | 0.20099 | 0.20801 | 0.21467 | 0.22097 | 0.22692 | 0.23251 | 0.23774 | 0.24264 | 0.24721 | 0.25145 | 0.25539 | 0.25904 | 0.26241 | 0.26551 | 0.26837 | 0.271 | 0.27341 | 0.27561 | 0.27762 | 0.27946 | 0.28114 | 0.28266 | 0.28405 | 0.2853 | 0.28644 | 0.28748 | 0.28841 | 0.28926 | 0.29002 | 0.29071 | 0.29133 | 0.29189 | 0.29239 | 0.29284 | 0.29325 | 0.29362 | 0.29394 | 0.29424 | 0.2945 | 0.29474 | 0.29495 | 0.29514 | 0.29531 | 0.29546 | 0.2956 | 0.29572 | 0.29583 | 0.29592 | 0.29601 | 0.29609 | 0.29616 | 0.29622 | 0.29627 | 0.29632 | 0.29637 | 0.2964 | 0.29644 | 0.29647 | 0.2965 | 0.29652 | 0.29654 | 0.29656 | 0.29658 | 0.2966 | 0.29661 | 0.29662 | 0.29663 | 0.29664 | 0.29665 | 0.29666 | 0.29667 | 0.29667 | 0.29668 | 0.29668 | 0.29669
| 34 | 76.7298 | 0.0092161 | 0.012034 | 0.015403 | 0.019354 | 0.023911 | 0.029084 | 0.03487 | 0.041254 | 0.048211 | 0.055703 | 0.063683 | 0.072096 | 0.080881 | 0.089973 | 0.099304 | 0.10881 | 0.11841 | 0.12805 | 0.13767 | 0.1472 | 0.15659 | 0.1658 | 0.17478 | 0.18349 | 0.19191 | 0.20001 | 0.20777 | 0.21517 | 0.22221 | 0.22888 | 0.23518 | 0.24111 | 0.24668 | 0.25189 | 0.25676 | 0.2613 | 0.26551 | 0.26942 | 0.27303 | 0.27637 | 0.27944 | 0.28227 | 0.28486 | 0.28724 | 0.28942 | 0.29141 | 0.29323 | 0.29488 | 0.29639 | 0.29776 | 0.299 | 0.30013 | 0.30115 | 0.30207 | 0.30291 | 0.30366 | 0.30434 | 0.30496 | 0.30551 | 0.30601 | 0.30646 | 0.30686 | 0.30723 | 0.30755 | 0.30785 | 0.30811 | 0.30834 | 0.30855 | 0.30874 | 0.30891 | 0.30906 | 0.3092 | 0.30932 | 0.30943 | 0.30953 | 0.30961 | 0.30969 | 0.30976 | 0.30982 | 0.30988 | 0.30992 | 0.30997 | 0.31001 | 0.31004 | 0.31007 | 0.3101 | 0.31013 | 0.31015 | 0.31017 | 0.31018 | 0.3102 | 0.31021 | 0.31023 | 0.31024 | 0.31025 | 0.31026 | 0.31026 | 0.31027 | 0.31028 | 0.31028 | 0.31029
| 35 | 77.8721 | 0.0092836 | 0.012133 | 0.015544 | 0.019551 | 0.024177 | 0.029437 | 0.03533 | 0.041841 | 0.048948 | 0.056612 | 0.064788 | 0.073422 | 0.082452 | 0.091813 | 0.10144 | 0.11125 | 0.12118 | 0.13117 | 0.14115 | 0.15106 | 0.16084 | 0.17044 | 0.17982 | 0.18893 | 0.19775 | 0.20625 | 0.2144 | 0.22219 | 0.22961 | 0.23665 | 0.24332 | 0.2496 | 0.2555 | 0.26104 | 0.26621 | 0.27104 | 0.27554 | 0.27971 | 0.28357 | 0.28714 | 0.29044 | 0.29348 | 0.29627 | 0.29883 | 0.30118 | 0.30333 | 0.30529 | 0.30708 | 0.30871 | 0.3102 | 0.31155 | 0.31277 | 0.31389 | 0.31489 | 0.31581 | 0.31663 | 0.31738 | 0.31805 | 0.31866 | 0.31921 | 0.3197 | 0.32014 | 0.32054 | 0.3209 | 0.32123 | 0.32152 | 0.32178 | 0.32201 | 0.32222 | 0.32241 | 0.32257 | 0.32273 | 0.32286 | 0.32298 | 0.32309 | 0.32319 | 0.32327 | 0.32335 | 0.32342 | 0.32348 | 0.32354 | 0.32359 | 0.32363 | 0.32367 | 0.3237 | 0.32373 | 0.32376 | 0.32379 | 0.32381 | 0.32383 | 0.32385 | 0.32386 | 0.32388 | 0.32389 | 0.3239 | 0.32391 | 0.32392 | 0.32393 | 0.32393 | 0.32394 | 0.32395
| 36 | 79.0144 | 0.0093456 | 0.012225 | 0.015675 | 0.019733 | 0.024426 | 0.029768 | 0.035761 | 0.042394 | 0.049642 | 0.057472 | 0.065837 | 0.074684 | 0.083951 | 0.093571 | 0.10348 | 0.11359 | 0.12385 | 0.13418 | 0.14452 | 0.1548 | 0.16496 | 0.17495 | 0.18472 | 0.19423 | 0.20345 | 0.21235 | 0.22089 | 0.22907 | 0.23688 | 0.24429 | 0.25132 | 0.25795 | 0.26419 | 0.27006 | 0.27555 | 0.28068 | 0.28545 | 0.2899 | 0.29402 | 0.29783 | 0.30136 | 0.30461 | 0.3076 | 0.31035 | 0.31287 | 0.31519 | 0.3173 | 0.31923 | 0.321 | 0.3226 | 0.32407 | 0.3254 | 0.3266 | 0.3277 | 0.32869 | 0.32959 | 0.3304 | 0.33114 | 0.3318 | 0.3324 | 0.33294 | 0.33343 | 0.33387 | 0.33426 | 0.33462 | 0.33494 | 0.33523 | 0.33548 | 0.33572 | 0.33592 | 0.33611 | 0.33628 | 0.33643 | 0.33656 | 0.33668 | 0.33679 | 0.33689 | 0.33697 | 0.33705 | 0.33712 | 0.33718 | 0.33723 | 0.33728 | 0.33733 | 0.33737 | 0.3374 | 0.33743 | 0.33746 | 0.33749 | 0.33751 | 0.33753 | 0.33755 | 0.33756 | 0.33758 | 0.33759 | 0.3376 | 0.33761 | 0.33762 | 0.33763 | 0.33764 | 0.33764
| 37 | 80.1567 | 0.0094027 | 0.012309 | 0.015796 | 0.019903 | 0.024658 | 0.030077 | 0.036165 | 0.042913 | 0.050297 | 0.058285 | 0.066831 | 0.075882 | 0.085377 | 0.095249 | 0.10543 | 0.11584 | 0.12642 | 0.13708 | 0.14777 | 0.15841 | 0.16894 | 0.17932 | 0.18948 | 0.19939 | 0.209 | 0.21829 | 0.22723 | 0.2358 | 0.24399 | 0.25178 | 0.25917 | 0.26616 | 0.27275 | 0.27894 | 0.28475 | 0.29018 | 0.29525 | 0.29997 | 0.30435 | 0.30841 | 0.31217 | 0.31564 | 0.31884 | 0.32179 | 0.32449 | 0.32697 | 0.32925 | 0.33133 | 0.33323 | 0.33496 | 0.33654 | 0.33797 | 0.33928 | 0.34047 | 0.34155 | 0.34252 | 0.34341 | 0.34421 | 0.34493 | 0.34558 | 0.34617 | 0.34671 | 0.34719 | 0.34762 | 0.34801 | 0.34836 | 0.34868 | 0.34896 | 0.34922 | 0.34944 | 0.34965 | 0.34983 | 0.35 | 0.35015 | 0.35028 | 0.3504 | 0.35051 | 0.3506 | 0.35069 | 0.35077 | 0.35084 | 0.3509 | 0.35095 | 0.351 | 0.35104 | 0.35108 | 0.35112 | 0.35115 | 0.35118 | 0.3512 | 0.35123 | 0.35125 | 0.35126 | 0.35128 | 0.35129 | 0.35131 | 0.35132 | 0.35133 | 0.35134 | 0.35135 | 0.35135
| 38 | 81.2991 | 0.009455 | 0.012387 | 0.015908 | 0.02006 | 0.024873 | 0.030366 | 0.036544 | 0.0434 | 0.050913 | 0.059051 | 0.067771 | 0.077018 | 0.086733 | 0.096848 | 0.10729 | 0.11799 | 0.12887 | 0.13986 | 0.15089 | 0.16189 | 0.17279 | 0.18354 | 0.19409 | 0.20439 | 0.2144 | 0.22408 | 0.23342 | 0.24237 | 0.25094 | 0.25911 | 0.26687 | 0.27421 | 0.28115 | 0.28767 | 0.2938 | 0.29954 | 0.30491 | 0.30991 | 0.31456 | 0.31887 | 0.32287 | 0.32657 | 0.32998 | 0.33312 | 0.33602 | 0.33867 | 0.34111 | 0.34334 | 0.34538 | 0.34724 | 0.34894 | 0.35049 | 0.3519 | 0.35318 | 0.35435 | 0.3554 | 0.35636 | 0.35723 | 0.35802 | 0.35873 | 0.35937 | 0.35995 | 0.36048 | 0.36095 | 0.36137 | 0.36176 | 0.3621 | 0.36242 | 0.3627 | 0.36295 | 0.36317 | 0.36338 | 0.36356 | 0.36372 | 0.36387 | 0.364 | 0.36412 | 0.36423 | 0.36432 | 0.36441 | 0.36448 | 0.36455 | 0.36461 | 0.36467 | 0.36472 | 0.36476 | 0.3648 | 0.36483 | 0.36487 | 0.36489 | 0.36492 | 0.36494 | 0.36496 | 0.36498 | 0.365 | 0.36501 | 0.36502 | 0.36503 | 0.36505 | 0.36505 | 0.36506
| 39 | 82.4414 | 0.009503 | 0.012458 | 0.016012 | 0.020206 | 0.025073 | 0.030635 | 0.036898 | 0.043857 | 0.051492 | 0.059774 | 0.068659 | 0.078094 | 0.08802 | 0.098369 | 0.10907 | 0.12005 | 0.13123 | 0.14253 | 0.15389 | 0.16524 | 0.1765 | 0.18763 | 0.19856 | 0.20924 | 0.21964 | 0.22971 | 0.23944 | 0.24878 | 0.25773 | 0.26627 | 0.2744 | 0.2821 | 0.28938 | 0.29625 | 0.3027 | 0.30875 | 0.31442 | 0.3197 | 0.32462 | 0.3292 | 0.33344 | 0.33737 | 0.34099 | 0.34434 | 0.34742 | 0.35026 | 0.35286 | 0.35525 | 0.35743 | 0.35943 | 0.36126 | 0.36292 | 0.36444 | 0.36582 | 0.36708 | 0.36822 | 0.36926 | 0.3702 | 0.37105 | 0.37182 | 0.37252 | 0.37315 | 0.37372 | 0.37423 | 0.3747 | 0.37512 | 0.37549 | 0.37583 | 0.37614 | 0.37642 | 0.37666 | 0.37689 | 0.37709 | 0.37727 | 0.37743 | 0.37757 | 0.3777 | 0.37782 | 0.37793 | 0.37802 | 0.37811 | 0.37818 | 0.37825 | 0.37831 | 0.37836 | 0.37841 | 0.37846 | 0.3785 | 0.37853 | 0.37856 | 0.37859 | 0.37862 | 0.37864 | 0.37866 | 0.37868 | 0.37869 | 0.37871 | 0.37872 | 0.37873 | 0.37874 | 0.37875
| 40 | 83.5837 | 0.009547 | 0.012524 | 0.016107 | 0.02034 | 0.025259 | 0.030885 | 0.037228 | 0.044284 | 0.052036 | 0.060454 | 0.069497 | 0.079112 | 0.089241 | 0.099814 | 0.11076 | 0.12201 | 0.13348 | 0.14509 | 0.15678 | 0.16846 | 0.18008 | 0.19157 | 0.20287 | 0.21393 | 0.22472 | 0.23518 | 0.24529 | 0.25502 | 0.26435 | 0.27326 | 0.28175 | 0.28982 | 0.29745 | 0.30465 | 0.31143 | 0.3178 | 0.32376 | 0.32934 | 0.33453 | 0.33937 | 0.34386 | 0.34802 | 0.35187 | 0.35543 | 0.3587 | 0.36172 | 0.3645 | 0.36704 | 0.36938 | 0.37152 | 0.37347 | 0.37526 | 0.37689 | 0.37837 | 0.37972 | 0.38095 | 0.38207 | 0.38308 | 0.384 | 0.38484 | 0.38559 | 0.38627 | 0.38689 | 0.38745 | 0.38796 | 0.38841 | 0.38882 | 0.38919 | 0.38953 | 0.38983 | 0.3901 | 0.39034 | 0.39056 | 0.39076 | 0.39094 | 0.3911 | 0.39124 | 0.39137 | 0.39149 | 0.39159 | 0.39168 | 0.39177 | 0.39184 | 0.39191 | 0.39197 | 0.39202 | 0.39207 | 0.39212 | 0.39216 | 0.39219 | 0.39222 | 0.39225 | 0.39227 | 0.3923 | 0.39232 | 0.39233 | 0.39235 | 0.39237 | 0.39238 | 0.39239 | 0.3924
| 41 | 84.726 | 0.0095873 | 0.012585 | 0.016195 | 0.020465 | 0.025431 | 0.031118 | 0.037536 | 0.044684 | 0.052546 | 0.061094 | 0.070287 | 0.080074 | 0.090396 | 0.10119 | 0.11237 | 0.12388 | 0.13562 | 0.14754 | 0.15954 | 0.17156 | 0.18352 | 0.19537 | 0.20703 | 0.21847 | 0.22963 | 0.24048 | 0.25097 | 0.26108 | 0.27079 | 0.28008 | 0.28893 | 0.29735 | 0.30534 | 0.31288 | 0.31999 | 0.32667 | 0.33294 | 0.3388 | 0.34428 | 0.34938 | 0.35412 | 0.35852 | 0.36259 | 0.36636 | 0.36984 | 0.37305 | 0.376 | 0.37871 | 0.3812 | 0.38348 | 0.38557 | 0.38748 | 0.38922 | 0.39081 | 0.39226 | 0.39358 | 0.39478 | 0.39587 | 0.39686 | 0.39776 | 0.39858 | 0.39932 | 0.39999 | 0.40059 | 0.40114 | 0.40163 | 0.40208 | 0.40248 | 0.40285 | 0.40317 | 0.40347 | 0.40374 | 0.40398 | 0.40419 | 0.40439 | 0.40456 | 0.40472 | 0.40486 | 0.40499 | 0.4051 | 0.4052 | 0.40529 | 0.40538 | 0.40545 | 0.40552 | 0.40558 | 0.40563 | 0.40568 | 0.40572 | 0.40576 | 0.4058 | 0.40583 | 0.40585 | 0.40588 | 0.4059 | 0.40592 | 0.40594 | 0.40596 | 0.40597 | 0.40598 | 0.40599
| 42 | 85.8683 | 0.0096241 | 0.01264 | 0.016276 | 0.02058 | 0.025591 | 0.031334 | 0.037824 | 0.045058 | 0.053024 | 0.061695 | 0.071031 | 0.080982 | 0.09149 | 0.10249 | 0.1139 | 0.12566 | 0.13767 | 0.14988 | 0.16218 | 0.17452 | 0.18683 | 0.19902 | 0.21105 | 0.22285 | 0.23439 | 0.24561 | 0.25648 | 0.26696 | 0.27705 | 0.28671 | 0.29593 | 0.30471 | 0.31304 | 0.32092 | 0.32836 | 0.33536 | 0.34193 | 0.34809 | 0.35385 | 0.35921 | 0.36421 | 0.36885 | 0.37316 | 0.37714 | 0.38082 | 0.38422 | 0.38735 | 0.39023 | 0.39288 | 0.3953 | 0.39753 | 0.39957 | 0.40143 | 0.40313 | 0.40468 | 0.40609 | 0.40738 | 0.40855 | 0.40962 | 0.41058 | 0.41146 | 0.41226 | 0.41298 | 0.41363 | 0.41422 | 0.41476 | 0.41524 | 0.41568 | 0.41607 | 0.41643 | 0.41675 | 0.41704 | 0.4173 | 0.41754 | 0.41775 | 0.41794 | 0.41811 | 0.41827 | 0.41841 | 0.41853 | 0.41864 | 0.41874 | 0.41884 | 0.41892 | 0.41899 | 0.41906 | 0.41911 | 0.41917 | 0.41922 | 0.41926 | 0.4193 | 0.41933 | 0.41936 | 0.41939 | 0.41941 | 0.41944 | 0.41946 | 0.41947 | 0.41949 | 0.4195 | 0.41952
| 43 | 87.0106 | 0.0096578 | 0.012691 | 0.01635 | 0.020686 | 0.025739 | 0.031535 | 0.038091 | 0.045407 | 0.053472 | 0.062259 | 0.071731 | 0.081839 | 0.092523 | 0.10372 | 0.11535 | 0.12735 | 0.13963 | 0.15211 | 0.16471 | 0.17737 | 0.19 | 0.20253 | 0.21491 | 0.22708 | 0.23898 | 0.25057 | 0.26181 | 0.27267 | 0.28312 | 0.29315 | 0.30273 | 0.31187 | 0.32055 | 0.32877 | 0.33654 | 0.34386 | 0.35074 | 0.35719 | 0.36323 | 0.36887 | 0.37412 | 0.37901 | 0.38354 | 0.38775 | 0.39164 | 0.39523 | 0.39854 | 0.40159 | 0.4044 | 0.40698 | 0.40934 | 0.41151 | 0.4135 | 0.41531 | 0.41696 | 0.41848 | 0.41985 | 0.42111 | 0.42225 | 0.42329 | 0.42423 | 0.42508 | 0.42586 | 0.42656 | 0.4272 | 0.42778 | 0.4283 | 0.42877 | 0.4292 | 0.42959 | 0.42993 | 0.43025 | 0.43053 | 0.43079 | 0.43102 | 0.43123 | 0.43141 | 0.43158 | 0.43173 | 0.43187 | 0.43199 | 0.4321 | 0.4322 | 0.43229 | 0.43237 | 0.43245 | 0.43251 | 0.43257 | 0.43262 | 0.43267 | 0.43271 | 0.43275 | 0.43278 | 0.43281 | 0.43284 | 0.43286 | 0.43289 | 0.43291 | 0.43292 | 0.43294 | 0.43295
| 44 | 88.1529 | 0.0096886 | 0.012738 | 0.016419 | 0.020785 | 0.025876 | 0.031722 | 0.03834 | 0.045733 | 0.05389 | 0.062788 | 0.072389 | 0.082645 | 0.093499 | 0.10488 | 0.11673 | 0.12896 | 0.14149 | 0.15424 | 0.16713 | 0.18009 | 0.19304 | 0.20591 | 0.21863 | 0.23115 | 0.2434 | 0.25536 | 0.26697 | 0.27819 | 0.28901 | 0.2994 | 0.30935 | 0.31884 | 0.32786 | 0.33642 | 0.34452 | 0.35216 | 0.35935 | 0.36609 | 0.37242 | 0.37833 | 0.38384 | 0.38897 | 0.39374 | 0.39817 | 0.40227 | 0.40606 | 0.40956 | 0.41279 | 0.41576 | 0.41849 | 0.421 | 0.4233 | 0.42541 | 0.42734 | 0.4291 | 0.43071 | 0.43218 | 0.43352 | 0.43474 | 0.43585 | 0.43686 | 0.43778 | 0.43861 | 0.43937 | 0.44006 | 0.44068 | 0.44124 | 0.44175 | 0.44221 | 0.44263 | 0.443 | 0.44334 | 0.44365 | 0.44393 | 0.44418 | 0.4444 | 0.44461 | 0.44479 | 0.44496 | 0.4451 | 0.44524 | 0.44536 | 0.44547 | 0.44556 | 0.44565 | 0.44573 | 0.4458 | 0.44587 | 0.44592 | 0.44598 | 0.44602 | 0.44606 | 0.4461 | 0.44613 | 0.44617 | 0.44619 | 0.44622 | 0.44624 | 0.44626 | 0.44628 | 0.44629
| 45 | 89.2952 | 0.0097167 | 0.01278 | 0.016482 | 0.020875 | 0.026002 | 0.031895 | 0.038571 | 0.046037 | 0.054281 | 0.063283 | 0.073006 | 0.083404 | 0.094419 | 0.10599 | 0.11803 | 0.13048 | 0.14325 | 0.15627 | 0.16944 | 0.18269 | 0.19595 | 0.20914 | 0.2222 | 0.23506 | 0.24767 | 0.25998 | 0.27195 | 0.28354 | 0.29472 | 0.30547 | 0.31577 | 0.32561 | 0.33498 | 0.34387 | 0.3523 | 0.36025 | 0.36775 | 0.3748 | 0.3814 | 0.38759 | 0.39336 | 0.39874 | 0.40375 | 0.4084 | 0.41272 | 0.41671 | 0.4204 | 0.4238 | 0.42694 | 0.42983 | 0.43248 | 0.43492 | 0.43716 | 0.43921 | 0.44108 | 0.44279 | 0.44436 | 0.44579 | 0.44709 | 0.44827 | 0.44935 | 0.45033 | 0.45123 | 0.45204 | 0.45277 | 0.45344 | 0.45404 | 0.45459 | 0.45509 | 0.45554 | 0.45594 | 0.45631 | 0.45664 | 0.45694 | 0.45721 | 0.45746 | 0.45768 | 0.45788 | 0.45806 | 0.45822 | 0.45836 | 0.45849 | 0.45861 | 0.45872 | 0.45882 | 0.4589 | 0.45898 | 0.45905 | 0.45911 | 0.45917 | 0.45922 | 0.45926 | 0.45931 | 0.45934 | 0.45938 | 0.45941 | 0.45943 | 0.45946 | 0.45948 | 0.4595 | 0.45952
| 46 | 90.4375 | 0.0097423 | 0.012819 | 0.01654 | 0.020958 | 0.026119 | 0.032055 | 0.038786 | 0.046319 | 0.054646 | 0.063746 | 0.073585 | 0.084117 | 0.095286 | 0.10703 | 0.11927 | 0.13193 | 0.14493 | 0.1582 | 0.17164 | 0.18518 | 0.19873 | 0.21224 | 0.22562 | 0.23882 | 0.25177 | 0.26443 | 0.27675 | 0.2887 | 0.30024 | 0.31134 | 0.32199 | 0.33218 | 0.34189 | 0.35112 | 0.35987 | 0.36815 | 0.37595 | 0.38329 | 0.39018 | 0.39664 | 0.40268 | 0.40831 | 0.41356 | 0.41844 | 0.42296 | 0.42716 | 0.43104 | 0.43463 | 0.43793 | 0.44098 | 0.44379 | 0.44636 | 0.44873 | 0.4509 | 0.45289 | 0.45471 | 0.45637 | 0.45789 | 0.45927 | 0.46054 | 0.46169 | 0.46273 | 0.46369 | 0.46455 | 0.46534 | 0.46605 | 0.4667 | 0.46729 | 0.46782 | 0.46831 | 0.46874 | 0.46914 | 0.4695 | 0.46982 | 0.47011 | 0.47038 | 0.47061 | 0.47083 | 0.47102 | 0.4712 | 0.47136 | 0.4715 | 0.47163 | 0.47174 | 0.47185 | 0.47194 | 0.47203 | 0.4721 | 0.47217 | 0.47223 | 0.47229 | 0.47234 | 0.47238 | 0.47242 | 0.47246 | 0.47249 | 0.47252 | 0.47255 | 0.47257 | 0.47259 | 0.47261
| 47 | 91.5798 | 0.0097657 | 0.012855 | 0.016593 | 0.021035 | 0.026227 | 0.032203 | 0.038986 | 0.046582 | 0.054987 | 0.06418 | 0.074128 | 0.084787 | 0.096102 | 0.10801 | 0.12043 | 0.1333 | 0.14652 | 0.16003 | 0.17373 | 0.18754 | 0.20139 | 0.2152 | 0.2289 | 0.24243 | 0.25572 | 0.26872 | 0.28139 | 0.29368 | 0.30557 | 0.31702 | 0.32802 | 0.33855 | 0.3486 | 0.35816 | 0.36724 | 0.37583 | 0.38394 | 0.39157 | 0.39875 | 0.40549 | 0.41179 | 0.41767 | 0.42316 | 0.42826 | 0.43301 | 0.43741 | 0.44148 | 0.44525 | 0.44873 | 0.45194 | 0.4549 | 0.45762 | 0.46012 | 0.46241 | 0.46451 | 0.46644 | 0.4682 | 0.46981 | 0.47128 | 0.47263 | 0.47385 | 0.47497 | 0.47598 | 0.47691 | 0.47775 | 0.47851 | 0.4792 | 0.47983 | 0.48041 | 0.48092 | 0.48139 | 0.48182 | 0.4822 | 0.48255 | 0.48286 | 0.48315 | 0.48341 | 0.48364 | 0.48385 | 0.48404 | 0.48421 | 0.48436 | 0.4845 | 0.48463 | 0.48474 | 0.48484 | 0.48493 | 0.48502 | 0.48509 | 0.48516 | 0.48522 | 0.48527 | 0.48532 | 0.48537 | 0.48541 | 0.48544 | 0.48548 | 0.4855 | 0.48553 | 0.48555 | 0.48558
| 48 | 92.7221 | 0.0097871 | 0.012888 | 0.016642 | 0.021105 | 0.026326 | 0.03234 | 0.039171 | 0.046827 | 0.055304 | 0.064585 | 0.074637 | 0.085416 | 0.096869 | 0.10893 | 0.12153 | 0.13459 | 0.14803 | 0.16177 | 0.17572 | 0.1898 | 0.20393 | 0.21804 | 0.23204 | 0.24589 | 0.2595 | 0.27284 | 0.28584 | 0.29848 | 0.31071 | 0.32251 | 0.33385 | 0.34472 | 0.35511 | 0.365 | 0.37439 | 0.3833 | 0.39171 | 0.39964 | 0.40711 | 0.41411 | 0.42068 | 0.42681 | 0.43254 | 0.43788 | 0.44284 | 0.44745 | 0.45172 | 0.45567 | 0.45933 | 0.4627 | 0.46581 | 0.46867 | 0.47131 | 0.47373 | 0.47595 | 0.47798 | 0.47985 | 0.48155 | 0.48311 | 0.48454 | 0.48584 | 0.48703 | 0.48811 | 0.48909 | 0.48999 | 0.4908 | 0.49154 | 0.49221 | 0.49282 | 0.49338 | 0.49388 | 0.49433 | 0.49475 | 0.49512 | 0.49546 | 0.49576 | 0.49604 | 0.49629 | 0.49652 | 0.49672 | 0.49691 | 0.49707 | 0.49722 | 0.49736 | 0.49748 | 0.49759 | 0.49769 | 0.49778 | 0.49786 | 0.49794 | 0.498 | 0.49806 | 0.49811 | 0.49816 | 0.49821 | 0.49825 | 0.49828 | 0.49831 | 0.49834 | 0.49837 | 0.49839
| 49 | 93.8644 | 0.0098065 | 0.012918 | 0.016686 | 0.02117 | 0.026418 | 0.032467 | 0.039342 | 0.047054 | 0.0556 | 0.064963 | 0.075113 | 0.086006 | 0.097591 | 0.1098 | 0.12257 | 0.13582 | 0.14946 | 0.16342 | 0.17761 | 0.19195 | 0.20635 | 0.22074 | 0.23505 | 0.2492 | 0.26313 | 0.2768 | 0.29013 | 0.30311 | 0.31568 | 0.32781 | 0.33949 | 0.35069 | 0.36141 | 0.37162 | 0.38134 | 0.39055 | 0.39927 | 0.40749 | 0.41524 | 0.42252 | 0.42935 | 0.43574 | 0.44171 | 0.44727 | 0.45245 | 0.45727 | 0.46174 | 0.46588 | 0.46971 | 0.47325 | 0.47651 | 0.47952 | 0.4823 | 0.48484 | 0.48718 | 0.48933 | 0.4913 | 0.4931 | 0.49475 | 0.49626 | 0.49764 | 0.4989 | 0.50004 | 0.50109 | 0.50204 | 0.50291 | 0.5037 | 0.50441 | 0.50507 | 0.50566 | 0.50619 | 0.50668 | 0.50712 | 0.50752 | 0.50788 | 0.50821 | 0.50851 | 0.50878 | 0.50902 | 0.50924 | 0.50944 | 0.50962 | 0.50978 | 0.50993 | 0.51006 | 0.51018 | 0.51029 | 0.51039 | 0.51047 | 0.51055 | 0.51062 | 0.51069 | 0.51075 | 0.5108 | 0.51085 | 0.51089 | 0.51093 | 0.51096 | 0.51099 | 0.51102 | 0.51105
| 50 | 95.0067 | 0.0098242 | 0.012945 | 0.016727 | 0.02123 | 0.026503 | 0.032585 | 0.039501 | 0.047265 | 0.055875 | 0.065316 | 0.075558 | 0.086559 | 0.098268 | 0.11062 | 0.12355 | 0.13697 | 0.15082 | 0.16499 | 0.17941 | 0.194 | 0.20866 | 0.22333 | 0.23792 | 0.25237 | 0.26661 | 0.28059 | 0.29425 | 0.30755 | 0.32045 | 0.33292 | 0.34493 | 0.35646 | 0.3675 | 0.37804 | 0.38807 | 0.39759 | 0.4066 | 0.41512 | 0.42315 | 0.43071 | 0.4378 | 0.44444 | 0.45065 | 0.45645 | 0.46185 | 0.46687 | 0.47154 | 0.47587 | 0.47987 | 0.48358 | 0.48701 | 0.49016 | 0.49307 | 0.49575 | 0.49822 | 0.50048 | 0.50255 | 0.50445 | 0.5062 | 0.50779 | 0.50925 | 0.51058 | 0.51179 | 0.5129 | 0.51391 | 0.51483 | 0.51567 | 0.51643 | 0.51713 | 0.51776 | 0.51833 | 0.51885 | 0.51932 | 0.51975 | 0.52013 | 0.52049 | 0.5208 | 0.52109 | 0.52135 | 0.52159 | 0.5218 | 0.522 | 0.52217 | 0.52233 | 0.52247 | 0.5226 | 0.52272 | 0.52282 | 0.52292 | 0.523 | 0.52308 | 0.52315 | 0.52321 | 0.52327 | 0.52332 | 0.52337 | 0.52341 | 0.52345 | 0.52348 | 0.52351 | 0.52354
| 51 | 96.149 | 0.0098403 | 0.01297 | 0.016765 | 0.021285 | 0.026581 | 0.032693 | 0.039648 | 0.047461 | 0.056132 | 0.065645 | 0.075973 | 0.087077 | 0.098904 | 0.11139 | 0.12447 | 0.13807 | 0.1521 | 0.16647 | 0.18112 | 0.19594 | 0.21086 | 0.22579 | 0.24066 | 0.2554 | 0.26995 | 0.28423 | 0.29821 | 0.31183 | 0.32505 | 0.33785 | 0.35018 | 0.36203 | 0.37339 | 0.38424 | 0.39458 | 0.40441 | 0.41372 | 0.42253 | 0.43084 | 0.43867 | 0.44602 | 0.45291 | 0.45937 | 0.46539 | 0.47101 | 0.47625 | 0.48111 | 0.48563 | 0.48982 | 0.49369 | 0.49728 | 0.50059 | 0.50364 | 0.50645 | 0.50903 | 0.51141 | 0.51359 | 0.5156 | 0.51743 | 0.51911 | 0.52065 | 0.52206 | 0.52334 | 0.52451 | 0.52558 | 0.52656 | 0.52745 | 0.52826 | 0.52899 | 0.52966 | 0.53027 | 0.53083 | 0.53133 | 0.53179 | 0.5322 | 0.53257 | 0.53291 | 0.53322 | 0.5335 | 0.53376 | 0.53399 | 0.53419 | 0.53438 | 0.53455 | 0.5347 | 0.53484 | 0.53497 | 0.53508 | 0.53518 | 0.53528 | 0.53536 | 0.53543 | 0.5355 | 0.53556 | 0.53562 | 0.53567 | 0.53572 | 0.53576 | 0.53579 | 0.53583 | 0.53586
| 52 | 97.2913 | 0.009855 | 0.012993 | 0.016799 | 0.021335 | 0.026652 | 0.032793 | 0.039784 | 0.047643 | 0.05637 | 0.065951 | 0.076362 | 0.087561 | 0.0995 | 0.11212 | 0.12534 | 0.1391 | 0.1533 | 0.16788 | 0.18273 | 0.19778 | 0.21294 | 0.22813 | 0.24328 | 0.2583 | 0.27314 | 0.28772 | 0.30201 | 0.31594 | 0.32947 | 0.34258 | 0.35524 | 0.36741 | 0.37908 | 0.39024 | 0.40089 | 0.41102 | 0.42063 | 0.42972 | 0.43831 | 0.4464 | 0.45402 | 0.46116 | 0.46785 | 0.47411 | 0.47995 | 0.4854 | 0.49046 | 0.49517 | 0.49954 | 0.50358 | 0.50733 | 0.51079 | 0.51398 | 0.51692 | 0.51963 | 0.52213 | 0.52442 | 0.52652 | 0.52846 | 0.53023 | 0.53185 | 0.53333 | 0.53468 | 0.53592 | 0.53705 | 0.53809 | 0.53903 | 0.53989 | 0.54067 | 0.54138 | 0.54202 | 0.54261 | 0.54315 | 0.54363 | 0.54407 | 0.54447 | 0.54484 | 0.54517 | 0.54546 | 0.54573 | 0.54598 | 0.5462 | 0.5464 | 0.54659 | 0.54675 | 0.5469 | 0.54703 | 0.54716 | 0.54727 | 0.54737 | 0.54746 | 0.54754 | 0.54761 | 0.54768 | 0.54774 | 0.54779 | 0.54784 | 0.54788 | 0.54792 | 0.54796 | 0.54799
| 53 | 98.4336 | 0.0098683 | 0.013014 | 0.016831 | 0.021381 | 0.026718 | 0.032885 | 0.03991 | 0.047812 | 0.056591 | 0.066237 | 0.076724 | 0.088014 | 0.10006 | 0.1128 | 0.12616 | 0.14007 | 0.15445 | 0.16921 | 0.18426 | 0.19953 | 0.21493 | 0.23037 | 0.24577 | 0.26107 | 0.27618 | 0.29106 | 0.30564 | 0.31988 | 0.33372 | 0.34714 | 0.3601 | 0.37259 | 0.38457 | 0.39604 | 0.40699 | 0.41741 | 0.42731 | 0.43669 | 0.44555 | 0.45391 | 0.46178 | 0.46918 | 0.47611 | 0.4826 | 0.48866 | 0.49431 | 0.49958 | 0.50448 | 0.50902 | 0.51324 | 0.51715 | 0.52076 | 0.52409 | 0.52717 | 0.53001 | 0.53262 | 0.53503 | 0.53723 | 0.53926 | 0.54112 | 0.54283 | 0.54439 | 0.54582 | 0.54712 | 0.54832 | 0.54941 | 0.5504 | 0.55131 | 0.55213 | 0.55289 | 0.55357 | 0.5542 | 0.55476 | 0.55528 | 0.55575 | 0.55617 | 0.55656 | 0.55691 | 0.55723 | 0.55752 | 0.55778 | 0.55802 | 0.55823 | 0.55843 | 0.5586 | 0.55876 | 0.55891 | 0.55904 | 0.55916 | 0.55926 | 0.55936 | 0.55945 | 0.55953 | 0.5596 | 0.55966 | 0.55972 | 0.55978 | 0.55982 | 0.55987 | 0.55991 | 0.55994
| 54 | 99.5759 | 0.0098804 | 0.013033 | 0.016859 | 0.021423 | 0.026779 | 0.03297 | 0.040027 | 0.047968 | 0.056796 | 0.066502 | 0.077062 | 0.088438 | 0.10058 | 0.11343 | 0.12693 | 0.14098 | 0.15552 | 0.17046 | 0.18571 | 0.20119 | 0.21681 | 0.23249 | 0.24814 | 0.2637 | 0.27909 | 0.29425 | 0.30912 | 0.32365 | 0.3378 | 0.35152 | 0.36479 | 0.37757 | 0.38986 | 0.40163 | 0.41287 | 0.42359 | 0.43378 | 0.44343 | 0.45257 | 0.4612 | 0.46933 | 0.47697 | 0.48414 | 0.49085 | 0.49714 | 0.503 | 0.50847 | 0.51355 | 0.51828 | 0.52267 | 0.52674 | 0.5305 | 0.53398 | 0.5372 | 0.54016 | 0.54289 | 0.54541 | 0.54772 | 0.54985 | 0.5518 | 0.55359 | 0.55523 | 0.55673 | 0.55811 | 0.55936 | 0.56051 | 0.56156 | 0.56252 | 0.56339 | 0.56419 | 0.56491 | 0.56557 | 0.56618 | 0.56672 | 0.56722 | 0.56767 | 0.56808 | 0.56846 | 0.5688 | 0.5691 | 0.56938 | 0.56964 | 0.56986 | 0.57007 | 0.57026 | 0.57043 | 0.57059 | 0.57073 | 0.57085 | 0.57097 | 0.57107 | 0.57117 | 0.57125 | 0.57133 | 0.5714 | 0.57146 | 0.57152 | 0.57157 | 0.57162 | 0.57166 | 0.5717
| 55 | 100.7182 | 0.0098915 | 0.01305 | 0.016886 | 0.021462 | 0.026835 | 0.033048 | 0.040134 | 0.048112 | 0.056987 | 0.066749 | 0.077377 | 0.088833 | 0.10107 | 0.11403 | 0.12765 | 0.14184 | 0.15654 | 0.17165 | 0.18709 | 0.20277 | 0.2186 | 0.23451 | 0.2504 | 0.26621 | 0.28187 | 0.2973 | 0.31245 | 0.32727 | 0.34171 | 0.35572 | 0.36929 | 0.38237 | 0.39495 | 0.40702 | 0.41856 | 0.42956 | 0.44003 | 0.44996 | 0.45937 | 0.46826 | 0.47664 | 0.48453 | 0.49193 | 0.49888 | 0.50538 | 0.51145 | 0.51712 | 0.52239 | 0.5273 | 0.53186 | 0.53609 | 0.54001 | 0.54364 | 0.54699 | 0.55008 | 0.55293 | 0.55556 | 0.55798 | 0.56021 | 0.56225 | 0.56413 | 0.56585 | 0.56743 | 0.56887 | 0.57019 | 0.5714 | 0.57251 | 0.57351 | 0.57444 | 0.57528 | 0.57604 | 0.57674 | 0.57738 | 0.57796 | 0.57848 | 0.57896 | 0.5794 | 0.57979 | 0.58015 | 0.58048 | 0.58078 | 0.58105 | 0.58129 | 0.58151 | 0.58172 | 0.5819 | 0.58206 | 0.58221 | 0.58235 | 0.58247 | 0.58258 | 0.58268 | 0.58277 | 0.58286 | 0.58293 | 0.583 | 0.58306 | 0.58311 | 0.58316 | 0.58321 | 0.58325
| 56 | 101.8605 | 0.0099015 | 0.013066 | 0.01691 | 0.021498 | 0.026886 | 0.03312 | 0.040233 | 0.048246 | 0.057164 | 0.066979 | 0.07767 | 0.089203 | 0.10153 | 0.11459 | 0.12832 | 0.14265 | 0.15749 | 0.17277 | 0.18838 | 0.20425 | 0.2203 | 0.23642 | 0.25255 | 0.26861 | 0.28452 | 0.30021 | 0.31564 | 0.33073 | 0.34545 | 0.35976 | 0.37361 | 0.38699 | 0.39986 | 0.41221 | 0.42403 | 0.43532 | 0.44607 | 0.45627 | 0.46595 | 0.47509 | 0.48373 | 0.49186 | 0.4995 | 0.50667 | 0.51339 | 0.51967 | 0.52553 | 0.531 | 0.53609 | 0.54082 | 0.54521 | 0.54928 | 0.55306 | 0.55654 | 0.55977 | 0.56274 | 0.56549 | 0.56801 | 0.57034 | 0.57247 | 0.57444 | 0.57624 | 0.57789 | 0.57941 | 0.5808 | 0.58207 | 0.58323 | 0.58429 | 0.58526 | 0.58615 | 0.58696 | 0.58769 | 0.58836 | 0.58898 | 0.58953 | 0.59004 | 0.5905 | 0.59092 | 0.5913 | 0.59165 | 0.59197 | 0.59225 | 0.59251 | 0.59275 | 0.59296 | 0.59316 | 0.59333 | 0.59349 | 0.59364 | 0.59377 | 0.59389 | 0.59399 | 0.59409 | 0.59418 | 0.59426 | 0.59433 | 0.5944 | 0.59446 | 0.59451 | 0.59456 | 0.5946
| 57 | 103.0028 | 0.0099106 | 0.01308 | 0.016932 | 0.02153 | 0.026933 | 0.033187 | 0.040325 | 0.04837 | 0.057328 | 0.067193 | 0.077944 | 0.089547 | 0.10196 | 0.11512 | 0.12896 | 0.14341 | 0.15839 | 0.17382 | 0.18961 | 0.20566 | 0.2219 | 0.23824 | 0.25459 | 0.27089 | 0.28704 | 0.30299 | 0.31868 | 0.33404 | 0.34904 | 0.36362 | 0.37776 | 0.39142 | 0.40457 | 0.41721 | 0.42931 | 0.44088 | 0.45189 | 0.46237 | 0.4723 | 0.48171 | 0.49059 | 0.49896 | 0.50683 | 0.51423 | 0.52116 | 0.52765 | 0.53371 | 0.53937 | 0.54464 | 0.54954 | 0.5541 | 0.55832 | 0.56224 | 0.56587 | 0.56922 | 0.57232 | 0.57518 | 0.57781 | 0.58024 | 0.58247 | 0.58452 | 0.58641 | 0.58814 | 0.58972 | 0.59118 | 0.59251 | 0.59373 | 0.59485 | 0.59587 | 0.5968 | 0.59765 | 0.59842 | 0.59913 | 0.59978 | 0.60037 | 0.6009 | 0.60139 | 0.60183 | 0.60224 | 0.60261 | 0.60294 | 0.60324 | 0.60352 | 0.60377 | 0.604 | 0.6042 | 0.60439 | 0.60456 | 0.60472 | 0.60485 | 0.60498 | 0.6051 | 0.6052 | 0.6053 | 0.60538 | 0.60546 | 0.60553 | 0.60559 | 0.60565 | 0.6057 | 0.60575
| 58 | 104.1451 | 0.0099189 | 0.013093 | 0.016952 | 0.02156 | 0.026976 | 0.033248 | 0.04041 | 0.048484 | 0.05748 | 0.067391 | 0.078198 | 0.089869 | 0.10236 | 0.11561 | 0.12956 | 0.14413 | 0.15924 | 0.17482 | 0.19076 | 0.207 | 0.22342 | 0.23996 | 0.25653 | 0.27305 | 0.28944 | 0.30564 | 0.32158 | 0.33721 | 0.35247 | 0.36733 | 0.38174 | 0.39567 | 0.40911 | 0.42202 | 0.4344 | 0.44623 | 0.45752 | 0.46825 | 0.47845 | 0.4881 | 0.49723 | 0.50584 | 0.51394 | 0.52156 | 0.5287 | 0.5354 | 0.54166 | 0.5475 | 0.55295 | 0.55803 | 0.56274 | 0.56713 | 0.57119 | 0.57495 | 0.57844 | 0.58166 | 0.58463 | 0.58737 | 0.5899 | 0.59223 | 0.59437 | 0.59634 | 0.59815 | 0.59981 | 0.60133 | 0.60273 | 0.60401 | 0.60518 | 0.60625 | 0.60722 | 0.60812 | 0.60893 | 0.60968 | 0.61036 | 0.61098 | 0.61154 | 0.61206 | 0.61253 | 0.61296 | 0.61334 | 0.6137 | 0.61402 | 0.61431 | 0.61458 | 0.61482 | 0.61504 | 0.61524 | 0.61542 | 0.61558 | 0.61573 | 0.61586 | 0.61599 | 0.6161 | 0.6162 | 0.61629 | 0.61637 | 0.61645 | 0.61652 | 0.61658 | 0.61663 | 0.61668
| 59 | 105.2874 | 0.0099264 | 0.013105 | 0.01697 | 0.021587 | 0.027016 | 0.033304 | 0.040488 | 0.04859 | 0.057621 | 0.067575 | 0.078435 | 0.090168 | 0.10273 | 0.11607 | 0.13011 | 0.1448 | 0.16004 | 0.17575 | 0.19185 | 0.20825 | 0.22486 | 0.2416 | 0.25837 | 0.27511 | 0.29173 | 0.30817 | 0.32435 | 0.34023 | 0.35575 | 0.37087 | 0.38555 | 0.39975 | 0.41346 | 0.42664 | 0.43928 | 0.45138 | 0.46293 | 0.47393 | 0.48438 | 0.49428 | 0.50365 | 0.51249 | 0.52082 | 0.52866 | 0.53602 | 0.54292 | 0.54937 | 0.5554 | 0.56103 | 0.56628 | 0.57116 | 0.57569 | 0.5799 | 0.5838 | 0.58742 | 0.59076 | 0.59385 | 0.5967 | 0.59933 | 0.60176 | 0.60399 | 0.60604 | 0.60793 | 0.60966 | 0.61126 | 0.61271 | 0.61405 | 0.61528 | 0.6164 | 0.61742 | 0.61836 | 0.61922 | 0.62 | 0.62072 | 0.62137 | 0.62197 | 0.62251 | 0.623 | 0.62345 | 0.62386 | 0.62424 | 0.62458 | 0.62489 | 0.62517 | 0.62542 | 0.62565 | 0.62587 | 0.62606 | 0.62623 | 0.62639 | 0.62653 | 0.62666 | 0.62678 | 0.62689 | 0.62699 | 0.62707 | 0.62715 | 0.62723 | 0.62729 | 0.62735 | 0.62741
| 60 | 106.4297 | 0.0099332 | 0.013116 | 0.016987 | 0.021612 | 0.027053 | 0.033356 | 0.040559 | 0.048688 | 0.057751 | 0.067746 | 0.078655 | 0.090447 | 0.10308 | 0.1165 | 0.13064 | 0.14543 | 0.16079 | 0.17664 | 0.19288 | 0.20944 | 0.22623 | 0.24315 | 0.26012 | 0.27706 | 0.2939 | 0.31057 | 0.32699 | 0.34312 | 0.35889 | 0.37427 | 0.3892 | 0.40367 | 0.41763 | 0.43108 | 0.44398 | 0.45635 | 0.46815 | 0.4794 | 0.4901 | 0.50024 | 0.50985 | 0.51892 | 0.52748 | 0.53553 | 0.5431 | 0.5502 | 0.55685 | 0.56307 | 0.56888 | 0.57429 | 0.57933 | 0.58402 | 0.58838 | 0.59242 | 0.59616 | 0.59963 | 0.60283 | 0.6058 | 0.60853 | 0.61105 | 0.61337 | 0.61551 | 0.61748 | 0.61929 | 0.62095 | 0.62247 | 0.62387 | 0.62515 | 0.62632 | 0.6274 | 0.62838 | 0.62928 | 0.6301 | 0.63085 | 0.63154 | 0.63216 | 0.63273 | 0.63325 | 0.63373 | 0.63416 | 0.63456 | 0.63491 | 0.63524 | 0.63554 | 0.63581 | 0.63605 | 0.63628 | 0.63648 | 0.63666 | 0.63683 | 0.63698 | 0.63712 | 0.63725 | 0.63736 | 0.63747 | 0.63756 | 0.63764 | 0.63772 | 0.63779 | 0.63786 | 0.63791
| 61 | 107.572 | 0.0099394 | 0.013126 | 0.017002 | 0.021635 | 0.027086 | 0.033403 | 0.040626 | 0.048778 | 0.057872 | 0.067904 | 0.078859 | 0.090707 | 0.1034 | 0.1169 | 0.13113 | 0.14602 | 0.16149 | 0.17747 | 0.19385 | 0.21057 | 0.22751 | 0.24461 | 0.26177 | 0.27892 | 0.29597 | 0.31286 | 0.32951 | 0.34587 | 0.36189 | 0.37751 | 0.3927 | 0.40741 | 0.42164 | 0.43534 | 0.4485 | 0.46112 | 0.47317 | 0.48467 | 0.49561 | 0.506 | 0.51584 | 0.52514 | 0.53392 | 0.54219 | 0.54996 | 0.55726 | 0.5641 | 0.5705 | 0.57649 | 0.58207 | 0.58727 | 0.59211 | 0.59662 | 0.60079 | 0.60467 | 0.60826 | 0.61158 | 0.61465 | 0.61749 | 0.62011 | 0.62252 | 0.62475 | 0.62679 | 0.62868 | 0.63041 | 0.632 | 0.63346 | 0.63479 | 0.63602 | 0.63714 | 0.63817 | 0.63911 | 0.63997 | 0.64076 | 0.64148 | 0.64214 | 0.64274 | 0.64328 | 0.64378 | 0.64424 | 0.64465 | 0.64503 | 0.64537 | 0.64569 | 0.64597 | 0.64623 | 0.64647 | 0.64668 | 0.64688 | 0.64706 | 0.64722 | 0.64736 | 0.6475 | 0.64762 | 0.64773 | 0.64783 | 0.64792 | 0.648 | 0.64807 | 0.64814 | 0.6482
| 62 | 108.7143 | 0.009945 | 0.013135 | 0.017016 | 0.021656 | 0.027117 | 0.033447 | 0.040687 | 0.048861 | 0.057983 | 0.068051 | 0.079049 | 0.090949 | 0.10371 | 0.11728 | 0.13159 | 0.14657 | 0.16215 | 0.17825 | 0.19477 | 0.21162 | 0.22873 | 0.246 | 0.26334 | 0.28068 | 0.29793 | 0.31503 | 0.3319 | 0.34849 | 0.36474 | 0.38061 | 0.39604 | 0.411 | 0.42547 | 0.43942 | 0.45284 | 0.4657 | 0.478 | 0.48974 | 0.50092 | 0.51154 | 0.52161 | 0.53114 | 0.54014 | 0.54862 | 0.5566 | 0.56409 | 0.57113 | 0.57771 | 0.58387 | 0.58962 | 0.59498 | 0.59998 | 0.60462 | 0.60894 | 0.61294 | 0.61666 | 0.6201 | 0.62328 | 0.62622 | 0.62893 | 0.63144 | 0.63375 | 0.63588 | 0.63783 | 0.63964 | 0.64129 | 0.64281 | 0.64421 | 0.64549 | 0.64666 | 0.64773 | 0.64872 | 0.64962 | 0.65044 | 0.65119 | 0.65188 | 0.65251 | 0.65309 | 0.65361 | 0.65409 | 0.65452 | 0.65492 | 0.65528 | 0.65561 | 0.65591 | 0.65619 | 0.65644 | 0.65666 | 0.65687 | 0.65706 | 0.65723 | 0.65738 | 0.65753 | 0.65765 | 0.65777 | 0.65788 | 0.65797 | 0.65806 | 0.65814 | 0.65821 | 0.65828
| 63 | 109.8566 | 0.0099501 | 0.013143 | 0.017028 | 0.021675 | 0.027145 | 0.033487 | 0.040743 | 0.048938 | 0.058087 | 0.068187 | 0.079226 | 0.091174 | 0.10399 | 0.11763 | 0.13202 | 0.14709 | 0.16277 | 0.17898 | 0.19563 | 0.21262 | 0.22988 | 0.24731 | 0.26483 | 0.28235 | 0.2998 | 0.3171 | 0.33418 | 0.35099 | 0.36747 | 0.38356 | 0.39923 | 0.41444 | 0.42915 | 0.44334 | 0.457 | 0.4701 | 0.48265 | 0.49463 | 0.50604 | 0.51689 | 0.52718 | 0.53693 | 0.54614 | 0.55483 | 0.56301 | 0.5707 | 0.57792 | 0.58469 | 0.59102 | 0.59694 | 0.60246 | 0.6076 | 0.61239 | 0.61685 | 0.62098 | 0.62482 | 0.62838 | 0.63167 | 0.63471 | 0.63752 | 0.64012 | 0.64252 | 0.64473 | 0.64676 | 0.64863 | 0.65035 | 0.65194 | 0.65339 | 0.65472 | 0.65594 | 0.65707 | 0.65809 | 0.65903 | 0.6599 | 0.66068 | 0.6614 | 0.66206 | 0.66266 | 0.66321 | 0.66372 | 0.66417 | 0.66459 | 0.66497 | 0.66532 | 0.66564 | 0.66592 | 0.66619 | 0.66643 | 0.66664 | 0.66684 | 0.66702 | 0.66719 | 0.66733 | 0.66747 | 0.66759 | 0.66771 | 0.66781 | 0.6679 | 0.66798 | 0.66806 | 0.66813
| 64 | 110.9989 | 0.0099548 | 0.01315 | 0.01704 | 0.021693 | 0.02717 | 0.033524 | 0.040795 | 0.049009 | 0.058182 | 0.068314 | 0.07939 | 0.091383 | 0.10425 | 0.11795 | 0.13242 | 0.14758 | 0.16336 | 0.17967 | 0.19644 | 0.21356 | 0.23096 | 0.24855 | 0.26623 | 0.28393 | 0.30156 | 0.31906 | 0.33635 | 0.35337 | 0.37007 | 0.38639 | 0.40228 | 0.41772 | 0.43266 | 0.44709 | 0.46099 | 0.47433 | 0.48711 | 0.49932 | 0.51096 | 0.52204 | 0.53255 | 0.54251 | 0.55194 | 0.56083 | 0.56921 | 0.5771 | 0.5845 | 0.59144 | 0.59795 | 0.60403 | 0.60971 | 0.615 | 0.61994 | 0.62453 | 0.62879 | 0.63275 | 0.63642 | 0.63982 | 0.64297 | 0.64588 | 0.64857 | 0.65105 | 0.65334 | 0.65545 | 0.6574 | 0.65919 | 0.66083 | 0.66234 | 0.66373 | 0.665 | 0.66617 | 0.66724 | 0.66822 | 0.66912 | 0.66995 | 0.6707 | 0.67139 | 0.67202 | 0.67259 | 0.67312 | 0.6736 | 0.67404 | 0.67444 | 0.6748 | 0.67513 | 0.67544 | 0.67571 | 0.67596 | 0.67619 | 0.6764 | 0.67659 | 0.67677 | 0.67692 | 0.67707 | 0.6772 | 0.67732 | 0.67742 | 0.67752 | 0.67761 | 0.67769 | 0.67776
| 65 | 112.1412 | 0.009959 | 0.013157 | 0.017051 | 0.021709 | 0.027194 | 0.033558 | 0.040842 | 0.049075 | 0.058271 | 0.06843 | 0.079542 | 0.091578 | 0.1045 | 0.11826 | 0.13279 | 0.14803 | 0.1639 | 0.18032 | 0.1972 | 0.21445 | 0.23198 | 0.24972 | 0.26756 | 0.28543 | 0.30324 | 0.32093 | 0.33841 | 0.35564 | 0.37254 | 0.38908 | 0.40519 | 0.42086 | 0.43603 | 0.45069 | 0.46481 | 0.47838 | 0.49139 | 0.50383 | 0.51569 | 0.52699 | 0.53772 | 0.5479 | 0.55752 | 0.56662 | 0.5752 | 0.58327 | 0.59086 | 0.59798 | 0.60465 | 0.6109 | 0.61673 | 0.62217 | 0.62725 | 0.63198 | 0.63637 | 0.64045 | 0.64424 | 0.64775 | 0.651 | 0.65401 | 0.65679 | 0.65936 | 0.66173 | 0.66392 | 0.66593 | 0.66779 | 0.66949 | 0.67106 | 0.67251 | 0.67383 | 0.67505 | 0.67616 | 0.67719 | 0.67812 | 0.67898 | 0.67977 | 0.68049 | 0.68115 | 0.68175 | 0.6823 | 0.6828 | 0.68326 | 0.68368 | 0.68406 | 0.68441 | 0.68473 | 0.68502 | 0.68528 | 0.68552 | 0.68574 | 0.68594 | 0.68613 | 0.68629 | 0.68644 | 0.68658 | 0.68671 | 0.68682 | 0.68692 | 0.68702 | 0.6871 | 0.68718
| 66 | 113.2836 | 0.0099628 | 0.013163 | 0.01706 | 0.021724 | 0.027216 | 0.033589 | 0.040886 | 0.049135 | 0.058352 | 0.068539 | 0.079683 | 0.091759 | 0.10473 | 0.11854 | 0.13314 | 0.14846 | 0.16441 | 0.18093 | 0.19791 | 0.21528 | 0.23295 | 0.25082 | 0.26881 | 0.28684 | 0.30483 | 0.3227 | 0.34037 | 0.35779 | 0.3749 | 0.39164 | 0.40797 | 0.42385 | 0.43925 | 0.45413 | 0.46847 | 0.48227 | 0.4955 | 0.50815 | 0.52024 | 0.53175 | 0.5427 | 0.55308 | 0.56291 | 0.5722 | 0.58097 | 0.58923 | 0.597 | 0.6043 | 0.61114 | 0.61754 | 0.62353 | 0.62912 | 0.63434 | 0.6392 | 0.64372 | 0.64792 | 0.65183 | 0.65545 | 0.6588 | 0.66191 | 0.66478 | 0.66744 | 0.66989 | 0.67215 | 0.67424 | 0.67616 | 0.67793 | 0.67956 | 0.68106 | 0.68243 | 0.6837 | 0.68486 | 0.68592 | 0.6869 | 0.68779 | 0.68861 | 0.68936 | 0.69005 | 0.69068 | 0.69125 | 0.69178 | 0.69226 | 0.6927 | 0.6931 | 0.69346 | 0.6938 | 0.6941 | 0.69438 | 0.69463 | 0.69486 | 0.69507 | 0.69527 | 0.69544 | 0.6956 | 0.69575 | 0.69588 | 0.696 | 0.69611 | 0.69621 | 0.6963 | 0.69638
| 67 | 114.4259 | 0.0099662 | 0.013169 | 0.017069 | 0.021737 | 0.027235 | 0.033618 | 0.040927 | 0.049191 | 0.058428 | 0.068639 | 0.079814 | 0.091927 | 0.10494 | 0.11881 | 0.13347 | 0.14886 | 0.16489 | 0.1815 | 0.19859 | 0.21607 | 0.23386 | 0.25186 | 0.27 | 0.28819 | 0.30633 | 0.32437 | 0.34223 | 0.35984 | 0.37714 | 0.39409 | 0.41062 | 0.42671 | 0.44232 | 0.45742 | 0.47198 | 0.48599 | 0.49943 | 0.51231 | 0.52461 | 0.53633 | 0.54748 | 0.55807 | 0.5681 | 0.57759 | 0.58654 | 0.59499 | 0.60293 | 0.6104 | 0.61741 | 0.62397 | 0.63011 | 0.63585 | 0.64121 | 0.6462 | 0.65085 | 0.65517 | 0.65919 | 0.66292 | 0.66638 | 0.66958 | 0.67254 | 0.67529 | 0.67782 | 0.68016 | 0.68232 | 0.68431 | 0.68614 | 0.68783 | 0.68938 | 0.69081 | 0.69212 | 0.69333 | 0.69443 | 0.69545 | 0.69638 | 0.69723 | 0.69802 | 0.69873 | 0.69939 | 0.69999 | 0.70054 | 0.70104 | 0.7015 | 0.70192 | 0.7023 | 0.70265 | 0.70297 | 0.70326 | 0.70352 | 0.70377 | 0.70399 | 0.70419 | 0.70437 | 0.70454 | 0.70469 | 0.70483 | 0.70496 | 0.70507 | 0.70518 | 0.70527 | 0.70536
| 68 | 115.5682 | 0.0099694 | 0.013174 | 0.017077 | 0.021749 | 0.027254 | 0.033644 | 0.040964 | 0.049242 | 0.058497 | 0.068732 | 0.079935 | 0.092083 | 0.10514 | 0.11906 | 0.13378 | 0.14923 | 0.16534 | 0.18203 | 0.19922 | 0.21681 | 0.23471 | 0.25285 | 0.27112 | 0.28945 | 0.30776 | 0.32596 | 0.344 | 0.36179 | 0.37928 | 0.39641 | 0.41315 | 0.42944 | 0.44526 | 0.46056 | 0.47533 | 0.48955 | 0.50321 | 0.51629 | 0.5288 | 0.54073 | 0.55208 | 0.56287 | 0.57309 | 0.58277 | 0.59192 | 0.60054 | 0.60866 | 0.6163 | 0.62346 | 0.63018 | 0.63648 | 0.64236 | 0.64785 | 0.65298 | 0.65775 | 0.6622 | 0.66633 | 0.67016 | 0.67372 | 0.67703 | 0.68008 | 0.68291 | 0.68553 | 0.68794 | 0.69017 | 0.69223 | 0.69413 | 0.69587 | 0.69748 | 0.69896 | 0.70032 | 0.70157 | 0.70272 | 0.70378 | 0.70475 | 0.70563 | 0.70645 | 0.70719 | 0.70788 | 0.7085 | 0.70907 | 0.7096 | 0.71008 | 0.71051 | 0.71091 | 0.71128 | 0.71161 | 0.71192 | 0.7122 | 0.71245 | 0.71268 | 0.71289 | 0.71308 | 0.71326 | 0.71342 | 0.71357 | 0.7137 | 0.71382 | 0.71393 | 0.71403 | 0.71412
| 69 | 116.7105 | 0.0099722 | 0.013179 | 0.017084 | 0.02176 | 0.02727 | 0.033668 | 0.040998 | 0.04929 | 0.058562 | 0.068817 | 0.080047 | 0.092228 | 0.10532 | 0.11929 | 0.13406 | 0.14958 | 0.16576 | 0.18254 | 0.19981 | 0.2175 | 0.23552 | 0.25378 | 0.27218 | 0.29065 | 0.30911 | 0.32747 | 0.34567 | 0.36363 | 0.38131 | 0.39863 | 0.41556 | 0.43205 | 0.44806 | 0.46356 | 0.47854 | 0.49297 | 0.50683 | 0.52011 | 0.53282 | 0.54495 | 0.5565 | 0.56748 | 0.5779 | 0.58777 | 0.59709 | 0.60589 | 0.61418 | 0.62198 | 0.62931 | 0.63619 | 0.64263 | 0.64865 | 0.65429 | 0.65954 | 0.66444 | 0.669 | 0.67325 | 0.67719 | 0.68085 | 0.68425 | 0.6874 | 0.69031 | 0.69301 | 0.6955 | 0.6978 | 0.69993 | 0.70189 | 0.7037 | 0.70536 | 0.70689 | 0.7083 | 0.7096 | 0.71079 | 0.71189 | 0.71289 | 0.71381 | 0.71466 | 0.71543 | 0.71614 | 0.71679 | 0.71739 | 0.71794 | 0.71844 | 0.71889 | 0.71931 | 0.71969 | 0.72004 | 0.72036 | 0.72065 | 0.72092 | 0.72116 | 0.72138 | 0.72158 | 0.72177 | 0.72193 | 0.72209 | 0.72223 | 0.72236 | 0.72247 | 0.72258 | 0.72267
| 70 | 117.8528 | 0.0099748 | 0.013183 | 0.017091 | 0.021771 | 0.027285 | 0.03369 | 0.041029 | 0.049333 | 0.058621 | 0.068897 | 0.080152 | 0.092363 | 0.1055 | 0.1195 | 0.13433 | 0.1499 | 0.16616 | 0.18301 | 0.20037 | 0.21816 | 0.23628 | 0.25465 | 0.27318 | 0.29179 | 0.31039 | 0.3289 | 0.34726 | 0.36539 | 0.38323 | 0.40074 | 0.41785 | 0.43453 | 0.45073 | 0.46643 | 0.48161 | 0.49623 | 0.51029 | 0.52378 | 0.53668 | 0.54901 | 0.56075 | 0.57192 | 0.58252 | 0.59257 | 0.60207 | 0.61105 | 0.61951 | 0.62747 | 0.63496 | 0.64199 | 0.64857 | 0.65474 | 0.66051 | 0.66589 | 0.67091 | 0.67559 | 0.67995 | 0.684 | 0.68776 | 0.69126 | 0.6945 | 0.6975 | 0.70027 | 0.70284 | 0.70522 | 0.70741 | 0.70943 | 0.7113 | 0.71302 | 0.7146 | 0.71606 | 0.71741 | 0.71864 | 0.71977 | 0.72082 | 0.72177 | 0.72265 | 0.72346 | 0.72419 | 0.72487 | 0.72549 | 0.72606 | 0.72658 | 0.72706 | 0.72749 | 0.72789 | 0.72825 | 0.72859 | 0.72889 | 0.72917 | 0.72942 | 0.72965 | 0.72987 | 0.73006 | 0.73023 | 0.7304 | 0.73054 | 0.73068 | 0.7308 | 0.73091 | 0.73101
| 71 | 118.9951 | 0.0099771 | 0.013187 | 0.017097 | 0.02178 | 0.027299 | 0.033711 | 0.041058 | 0.049374 | 0.058676 | 0.06897 | 0.080248 | 0.092488 | 0.10565 | 0.1197 | 0.13458 | 0.15021 | 0.16652 | 0.18345 | 0.20089 | 0.21877 | 0.23699 | 0.25547 | 0.27412 | 0.29286 | 0.31159 | 0.33025 | 0.34876 | 0.36705 | 0.38507 | 0.40274 | 0.42003 | 0.43689 | 0.45328 | 0.46917 | 0.48454 | 0.49935 | 0.5136 | 0.52728 | 0.54038 | 0.55289 | 0.56483 | 0.57618 | 0.58697 | 0.59719 | 0.60687 | 0.61601 | 0.62464 | 0.63276 | 0.64041 | 0.64758 | 0.65432 | 0.66062 | 0.66652 | 0.67203 | 0.67718 | 0.68197 | 0.68644 | 0.6906 | 0.69446 | 0.69805 | 0.70138 | 0.70446 | 0.70732 | 0.70997 | 0.71241 | 0.71467 | 0.71676 | 0.71869 | 0.72046 | 0.7221 | 0.72361 | 0.72499 | 0.72627 | 0.72745 | 0.72853 | 0.72952 | 0.73043 | 0.73126 | 0.73203 | 0.73273 | 0.73338 | 0.73397 | 0.73451 | 0.735 | 0.73546 | 0.73587 | 0.73625 | 0.7366 | 0.73692 | 0.73721 | 0.73747 | 0.73771 | 0.73794 | 0.73814 | 0.73832 | 0.73849 | 0.73864 | 0.73878 | 0.73891 | 0.73903 | 0.73914
| 72 | 120.1374 | 0.0099793 | 0.01319 | 0.017103 | 0.021788 | 0.027312 | 0.033729 | 0.041085 | 0.049411 | 0.058727 | 0.069038 | 0.080338 | 0.092604 | 0.1058 | 0.11989 | 0.13481 | 0.15049 | 0.16687 | 0.18386 | 0.20138 | 0.21935 | 0.23766 | 0.25625 | 0.27501 | 0.29387 | 0.31273 | 0.33153 | 0.35019 | 0.36863 | 0.38681 | 0.40465 | 0.42211 | 0.43914 | 0.45571 | 0.47179 | 0.48733 | 0.50234 | 0.51677 | 0.53064 | 0.54392 | 0.55662 | 0.56874 | 0.58027 | 0.59124 | 0.60164 | 0.61148 | 0.62079 | 0.62958 | 0.63787 | 0.64566 | 0.65298 | 0.65986 | 0.6663 | 0.67233 | 0.67797 | 0.68323 | 0.68815 | 0.69272 | 0.69698 | 0.70095 | 0.70463 | 0.70805 | 0.71122 | 0.71416 | 0.71688 | 0.71939 | 0.72172 | 0.72387 | 0.72586 | 0.72769 | 0.72938 | 0.73094 | 0.73237 | 0.73369 | 0.73491 | 0.73602 | 0.73705 | 0.73799 | 0.73886 | 0.73965 | 0.74038 | 0.74105 | 0.74167 | 0.74223 | 0.74274 | 0.74321 | 0.74365 | 0.74404 | 0.7444 | 0.74473 | 0.74504 | 0.74531 | 0.74557 | 0.7458 | 0.74601 | 0.7462 | 0.74638 | 0.74654 | 0.74668 | 0.74682 | 0.74694 | 0.74705
| 73 | 121.2797 | 0.0099812 | 0.013193 | 0.017108 | 0.021796 | 0.027324 | 0.033746 | 0.041109 | 0.049445 | 0.058773 | 0.069101 | 0.08042 | 0.092711 | 0.10594 | 0.12006 | 0.13502 | 0.15076 | 0.16719 | 0.18425 | 0.20184 | 0.21989 | 0.2383 | 0.25698 | 0.27585 | 0.29482 | 0.31381 | 0.33274 | 0.35154 | 0.37013 | 0.38846 | 0.40646 | 0.42408 | 0.44129 | 0.45803 | 0.47428 | 0.49 | 0.50519 | 0.51981 | 0.53385 | 0.54732 | 0.5602 | 0.57249 | 0.5842 | 0.59534 | 0.60591 | 0.61592 | 0.62539 | 0.63434 | 0.64278 | 0.65072 | 0.65819 | 0.6652 | 0.67178 | 0.67794 | 0.6837 | 0.68909 | 0.69411 | 0.6988 | 0.70316 | 0.70723 | 0.711 | 0.71451 | 0.71776 | 0.72078 | 0.72358 | 0.72616 | 0.72856 | 0.73077 | 0.73282 | 0.73471 | 0.73645 | 0.73805 | 0.73953 | 0.7409 | 0.74215 | 0.74331 | 0.74437 | 0.74535 | 0.74624 | 0.74707 | 0.74782 | 0.74852 | 0.74915 | 0.74974 | 0.75027 | 0.75076 | 0.75121 | 0.75162 | 0.752 | 0.75234 | 0.75266 | 0.75295 | 0.75321 | 0.75345 | 0.75367 | 0.75387 | 0.75406 | 0.75422 | 0.75438 | 0.75452 | 0.75465 | 0.75476
| 74 | 122.422 | 0.0099829 | 0.013196 | 0.017112 | 0.021803 | 0.027334 | 0.033762 | 0.041132 | 0.049476 | 0.058816 | 0.069159 | 0.080497 | 0.092811 | 0.10607 | 0.12022 | 0.13522 | 0.151 | 0.16749 | 0.18461 | 0.20227 | 0.2204 | 0.23889 | 0.25767 | 0.27664 | 0.29572 | 0.31483 | 0.33389 | 0.35282 | 0.37155 | 0.39002 | 0.40818 | 0.42596 | 0.44333 | 0.46024 | 0.47665 | 0.49255 | 0.50791 | 0.5227 | 0.53693 | 0.55056 | 0.56362 | 0.57608 | 0.58797 | 0.59927 | 0.61001 | 0.62019 | 0.62982 | 0.63892 | 0.64751 | 0.6556 | 0.66321 | 0.67036 | 0.67707 | 0.68336 | 0.68924 | 0.69474 | 0.69988 | 0.70467 | 0.70914 | 0.7133 | 0.71717 | 0.72076 | 0.7241 | 0.7272 | 0.73007 | 0.73273 | 0.73519 | 0.73747 | 0.73957 | 0.74152 | 0.74331 | 0.74496 | 0.74649 | 0.7479 | 0.74919 | 0.75039 | 0.75148 | 0.75249 | 0.75342 | 0.75427 | 0.75506 | 0.75577 | 0.75643 | 0.75704 | 0.75759 | 0.7581 | 0.75857 | 0.759 | 0.75939 | 0.75975 | 0.76007 | 0.76037 | 0.76065 | 0.7609 | 0.76113 | 0.76134 | 0.76153 | 0.76171 | 0.76187 | 0.76201 | 0.76215 | 0.76227
| 75 | 123.5643 | 0.0099845 | 0.013199 | 0.017116 | 0.02181 | 0.027344 | 0.033776 | 0.041152 | 0.049505 | 0.058856 | 0.069212 | 0.080568 | 0.092904 | 0.10619 | 0.12037 | 0.13541 | 0.15124 | 0.16777 | 0.18495 | 0.20268 | 0.22087 | 0.23945 | 0.25831 | 0.27738 | 0.29657 | 0.31579 | 0.33497 | 0.35403 | 0.37289 | 0.39151 | 0.40981 | 0.42774 | 0.44527 | 0.46234 | 0.47892 | 0.49498 | 0.51051 | 0.52547 | 0.53986 | 0.55367 | 0.5669 | 0.57953 | 0.59158 | 0.60305 | 0.61395 | 0.62428 | 0.63407 | 0.64333 | 0.65206 | 0.6603 | 0.66805 | 0.67533 | 0.68217 | 0.68858 | 0.69459 | 0.7002 | 0.70545 | 0.71035 | 0.71492 | 0.71918 | 0.72314 | 0.72682 | 0.73024 | 0.73342 | 0.73636 | 0.73909 | 0.74162 | 0.74396 | 0.74612 | 0.74812 | 0.74997 | 0.75167 | 0.75324 | 0.75469 | 0.75603 | 0.75726 | 0.75839 | 0.75943 | 0.76039 | 0.76127 | 0.76208 | 0.76283 | 0.76351 | 0.76414 | 0.76471 | 0.76524 | 0.76572 | 0.76617 | 0.76657 | 0.76695 | 0.76729 | 0.7676 | 0.76788 | 0.76815 | 0.76839 | 0.7686 | 0.7688 | 0.76899 | 0.76915 | 0.76931 | 0.76945 | 0.76957
| 76 | 124.7066 | 0.009986 | 0.013201 | 0.01712 | 0.021816 | 0.027353 | 0.03379 | 0.041171 | 0.049532 | 0.058893 | 0.069262 | 0.080634 | 0.09299 | 0.1063 | 0.12051 | 0.13559 | 0.15145 | 0.16804 | 0.18527 | 0.20305 | 0.22132 | 0.23997 | 0.25892 | 0.27809 | 0.29737 | 0.3167 | 0.33599 | 0.35517 | 0.37417 | 0.39292 | 0.41136 | 0.42944 | 0.44711 | 0.46434 | 0.48107 | 0.4973 | 0.51299 | 0.52811 | 0.54267 | 0.55665 | 0.57003 | 0.58283 | 0.59504 | 0.60667 | 0.61773 | 0.62822 | 0.63816 | 0.64756 | 0.65644 | 0.66482 | 0.6727 | 0.68012 | 0.68709 | 0.69362 | 0.69975 | 0.70548 | 0.71084 | 0.71584 | 0.72051 | 0.72486 | 0.72891 | 0.73268 | 0.73618 | 0.73943 | 0.74245 | 0.74525 | 0.74785 | 0.75025 | 0.75247 | 0.75452 | 0.75642 | 0.75818 | 0.75979 | 0.76129 | 0.76266 | 0.76393 | 0.7651 | 0.76618 | 0.76717 | 0.76808 | 0.76891 | 0.76968 | 0.77039 | 0.77104 | 0.77163 | 0.77218 | 0.77268 | 0.77314 | 0.77356 | 0.77395 | 0.7743 | 0.77463 | 0.77492 | 0.77519 | 0.77544 | 0.77567 | 0.77588 | 0.77607 | 0.77624 | 0.7764 | 0.77655 | 0.77668
| 77 | 125.8489 | 0.0099873 | 0.013203 | 0.017124 | 0.021821 | 0.027361 | 0.033802 | 0.041188 | 0.049556 | 0.058926 | 0.069308 | 0.080695 | 0.093069 | 0.1064 | 0.12064 | 0.13575 | 0.15165 | 0.16828 | 0.18556 | 0.20341 | 0.22174 | 0.24046 | 0.2595 | 0.27874 | 0.29813 | 0.31756 | 0.33696 | 0.35626 | 0.37537 | 0.39425 | 0.41283 | 0.43105 | 0.44886 | 0.46624 | 0.48313 | 0.49951 | 0.51535 | 0.53064 | 0.54535 | 0.55949 | 0.57303 | 0.58599 | 0.59836 | 0.61015 | 0.62135 | 0.632 | 0.64208 | 0.65163 | 0.66065 | 0.66917 | 0.67719 | 0.68473 | 0.69182 | 0.69848 | 0.70472 | 0.71056 | 0.71603 | 0.72114 | 0.7259 | 0.73035 | 0.73449 | 0.73834 | 0.74193 | 0.74526 | 0.74835 | 0.75122 | 0.75388 | 0.75634 | 0.75862 | 0.76073 | 0.76268 | 0.76448 | 0.76615 | 0.76768 | 0.7691 | 0.77041 | 0.77161 | 0.77272 | 0.77374 | 0.77468 | 0.77554 | 0.77634 | 0.77707 | 0.77774 | 0.77835 | 0.77892 | 0.77944 | 0.77991 | 0.78035 | 0.78075 | 0.78112 | 0.78146 | 0.78176 | 0.78205 | 0.7823 | 0.78254 | 0.78276 | 0.78296 | 0.78314 | 0.7833 | 0.78346 | 0.78359
| 78 | 126.9912 | 0.0099884 | 0.013205 | 0.017127 | 0.021826 | 0.027369 | 0.033813 | 0.041204 | 0.049579 | 0.058958 | 0.06935 | 0.080751 | 0.093143 | 0.10649 | 0.12077 | 0.1359 | 0.15184 | 0.16851 | 0.18584 | 0.20374 | 0.22213 | 0.24093 | 0.26003 | 0.27937 | 0.29884 | 0.31837 | 0.33787 | 0.35728 | 0.37652 | 0.39552 | 0.41422 | 0.43257 | 0.45053 | 0.46805 | 0.48508 | 0.50161 | 0.51761 | 0.53304 | 0.54791 | 0.5622 | 0.5759 | 0.58901 | 0.60154 | 0.61347 | 0.62483 | 0.63562 | 0.64585 | 0.65554 | 0.6647 | 0.67335 | 0.6815 | 0.68917 | 0.69639 | 0.70316 | 0.70952 | 0.71547 | 0.72104 | 0.72625 | 0.73111 | 0.73565 | 0.73988 | 0.74382 | 0.74748 | 0.75089 | 0.75406 | 0.75699 | 0.75972 | 0.76224 | 0.76458 | 0.76674 | 0.76875 | 0.7706 | 0.77231 | 0.77389 | 0.77534 | 0.77669 | 0.77793 | 0.77907 | 0.78012 | 0.78109 | 0.78198 | 0.7828 | 0.78355 | 0.78425 | 0.78488 | 0.78547 | 0.786 | 0.7865 | 0.78695 | 0.78736 | 0.78774 | 0.78809 | 0.78841 | 0.78871 | 0.78897 | 0.78922 | 0.78944 | 0.78965 | 0.78984 | 0.79001 | 0.79017 | 0.79031
| 79 | 128.1335 | 0.0099895 | 0.013207 | 0.01713 | 0.02183 | 0.027376 | 0.033823 | 0.041219 | 0.049599 | 0.058986 | 0.069389 | 0.080803 | 0.093211 | 0.10658 | 0.12088 | 0.13604 | 0.15201 | 0.16873 | 0.1861 | 0.20405 | 0.2225 | 0.24136 | 0.26054 | 0.27995 | 0.29951 | 0.31913 | 0.33873 | 0.35825 | 0.37759 | 0.39671 | 0.41554 | 0.43402 | 0.45211 | 0.46977 | 0.48694 | 0.50361 | 0.51975 | 0.53534 | 0.55036 | 0.5648 | 0.57865 | 0.59191 | 0.60458 | 0.61666 | 0.62817 | 0.6391 | 0.64947 | 0.6593 | 0.66859 | 0.67737 | 0.68565 | 0.69345 | 0.70078 | 0.70767 | 0.71414 | 0.7202 | 0.72588 | 0.73119 | 0.73614 | 0.74077 | 0.74509 | 0.74911 | 0.75286 | 0.75634 | 0.75957 | 0.76258 | 0.76537 | 0.76795 | 0.77035 | 0.77257 | 0.77462 | 0.77652 | 0.77828 | 0.7799 | 0.7814 | 0.78278 | 0.78405 | 0.78523 | 0.78631 | 0.78731 | 0.78823 | 0.78907 | 0.78985 | 0.79056 | 0.79122 | 0.79182 | 0.79238 | 0.79289 | 0.79336 | 0.79378 | 0.79418 | 0.79454 | 0.79487 | 0.79517 | 0.79545 | 0.79571 | 0.79594 | 0.79616 | 0.79635 | 0.79653 | 0.7967 | 0.79685
| 80 | 129.2758 | 0.0099905 | 0.013209 | 0.017132 | 0.021835 | 0.027382 | 0.033832 | 0.041233 | 0.049619 | 0.059013 | 0.069425 | 0.080851 | 0.093274 | 0.10667 | 0.12098 | 0.13617 | 0.15218 | 0.16893 | 0.18634 | 0.20434 | 0.22285 | 0.24177 | 0.26101 | 0.2805 | 0.30014 | 0.31985 | 0.33955 | 0.35916 | 0.37862 | 0.39785 | 0.41679 | 0.4354 | 0.45362 | 0.4714 | 0.48871 | 0.50552 | 0.5218 | 0.53753 | 0.55269 | 0.56728 | 0.58127 | 0.59468 | 0.60749 | 0.61972 | 0.63136 | 0.64243 | 0.65294 | 0.6629 | 0.67233 | 0.68124 | 0.68964 | 0.69756 | 0.70501 | 0.71202 | 0.71859 | 0.72476 | 0.73054 | 0.73595 | 0.741 | 0.74572 | 0.75012 | 0.75422 | 0.75805 | 0.7616 | 0.76491 | 0.76798 | 0.77084 | 0.77348 | 0.77594 | 0.77821 | 0.78031 | 0.78226 | 0.78406 | 0.78572 | 0.78726 | 0.78868 | 0.78999 | 0.7912 | 0.79231 | 0.79334 | 0.79428 | 0.79516 | 0.79596 | 0.79669 | 0.79737 | 0.79799 | 0.79857 | 0.79909 | 0.79958 | 0.80002 | 0.80043 | 0.8008 | 0.80114 | 0.80146 | 0.80175 | 0.80201 | 0.80225 | 0.80248 | 0.80268 | 0.80287 | 0.80304 | 0.80319
| 81 | 130.4181 | 0.0099914 | 0.01321 | 0.017135 | 0.021838 | 0.027388 | 0.033841 | 0.041245 | 0.049636 | 0.059037 | 0.069458 | 0.080896 | 0.093333 | 0.10674 | 0.12108 | 0.1363 | 0.15233 | 0.16911 | 0.18657 | 0.20462 | 0.22317 | 0.24215 | 0.26146 | 0.28102 | 0.30073 | 0.32053 | 0.34032 | 0.36002 | 0.37958 | 0.39892 | 0.41798 | 0.4367 | 0.45504 | 0.47295 | 0.49039 | 0.50734 | 0.52375 | 0.53962 | 0.55492 | 0.56964 | 0.58378 | 0.59732 | 0.61027 | 0.62264 | 0.63442 | 0.64563 | 0.65627 | 0.66636 | 0.67592 | 0.68495 | 0.69347 | 0.70151 | 0.70908 | 0.7162 | 0.72288 | 0.72916 | 0.73503 | 0.74054 | 0.74568 | 0.75049 | 0.75498 | 0.75916 | 0.76306 | 0.76669 | 0.77007 | 0.77321 | 0.77612 | 0.77883 | 0.78134 | 0.78367 | 0.78582 | 0.78782 | 0.78966 | 0.79137 | 0.79295 | 0.7944 | 0.79575 | 0.79699 | 0.79813 | 0.79919 | 0.80016 | 0.80106 | 0.80188 | 0.80264 | 0.80334 | 0.80398 | 0.80457 | 0.80512 | 0.80561 | 0.80607 | 0.80649 | 0.80688 | 0.80723 | 0.80756 | 0.80786 | 0.80813 | 0.80838 | 0.80861 | 0.80882 | 0.80902 | 0.8092 | 0.80936
| 82 | 131.5604 | 0.0099922 | 0.013212 | 0.017137 | 0.021842 | 0.027393 | 0.033849 | 0.041256 | 0.049652 | 0.05906 | 0.069489 | 0.080937 | 0.093387 | 0.10681 | 0.12117 | 0.13641 | 0.15247 | 0.16929 | 0.18678 | 0.20487 | 0.22348 | 0.24251 | 0.26188 | 0.2815 | 0.30129 | 0.32116 | 0.34104 | 0.36084 | 0.38049 | 0.39994 | 0.4191 | 0.43794 | 0.4564 | 0.47443 | 0.49199 | 0.50906 | 0.52561 | 0.54161 | 0.55704 | 0.5719 | 0.58617 | 0.59985 | 0.61294 | 0.62544 | 0.63735 | 0.64869 | 0.65946 | 0.66968 | 0.67936 | 0.68851 | 0.69716 | 0.70531 | 0.713 | 0.72022 | 0.72701 | 0.73339 | 0.73936 | 0.74496 | 0.7502 | 0.75509 | 0.75966 | 0.76393 | 0.7679 | 0.77161 | 0.77505 | 0.77826 | 0.78124 | 0.784 | 0.78657 | 0.78895 | 0.79115 | 0.79319 | 0.79508 | 0.79683 | 0.79845 | 0.79994 | 0.80132 | 0.8026 | 0.80377 | 0.80486 | 0.80586 | 0.80678 | 0.80763 | 0.80841 | 0.80913 | 0.80979 | 0.8104 | 0.81096 | 0.81147 | 0.81195 | 0.81238 | 0.81278 | 0.81315 | 0.81348 | 0.81379 | 0.81407 | 0.81433 | 0.81457 | 0.81479 | 0.81499 | 0.81518 | 0.81534
| 83 | 132.7027 | 0.0099929 | 0.013213 | 0.017139 | 0.021845 | 0.027398 | 0.033856 | 0.041267 | 0.049667 | 0.05908 | 0.069517 | 0.080975 | 0.093438 | 0.10688 | 0.12125 | 0.13651 | 0.1526 | 0.16945 | 0.18698 | 0.20511 | 0.22376 | 0.24284 | 0.26227 | 0.28196 | 0.30182 | 0.32177 | 0.34172 | 0.36161 | 0.38136 | 0.4009 | 0.42017 | 0.43911 | 0.45768 | 0.47583 | 0.49351 | 0.51071 | 0.52738 | 0.5435 | 0.55907 | 0.57405 | 0.58845 | 0.60226 | 0.61548 | 0.62811 | 0.64016 | 0.65162 | 0.66252 | 0.67286 | 0.68266 | 0.69194 | 0.7007 | 0.70897 | 0.71676 | 0.72409 | 0.73099 | 0.73746 | 0.74353 | 0.74922 | 0.75455 | 0.75953 | 0.76418 | 0.76853 | 0.77258 | 0.77635 | 0.77987 | 0.78314 | 0.78618 | 0.789 | 0.79162 | 0.79405 | 0.79631 | 0.7984 | 0.80033 | 0.80212 | 0.80378 | 0.80531 | 0.80673 | 0.80803 | 0.80924 | 0.81035 | 0.81138 | 0.81232 | 0.8132 | 0.814 | 0.81474 | 0.81542 | 0.81605 | 0.81663 | 0.81716 | 0.81764 | 0.81809 | 0.8185 | 0.81888 | 0.81923 | 0.81955 | 0.81984 | 0.82011 | 0.82036 | 0.82058 | 0.82079 | 0.82098 | 0.82115
| 84 | 133.845 | 0.0099935 | 0.013214 | 0.017141 | 0.021848 | 0.027402 | 0.033862 | 0.041276 | 0.049681 | 0.0591 | 0.069543 | 0.08101 | 0.093484 | 0.10694 | 0.12133 | 0.13661 | 0.15273 | 0.1696 | 0.18716 | 0.20533 | 0.22403 | 0.24316 | 0.26264 | 0.28239 | 0.30231 | 0.32233 | 0.34237 | 0.36234 | 0.38217 | 0.40181 | 0.42117 | 0.44022 | 0.4589 | 0.47716 | 0.49496 | 0.51227 | 0.52906 | 0.54531 | 0.56099 | 0.57611 | 0.59063 | 0.60457 | 0.61792 | 0.63067 | 0.64284 | 0.65443 | 0.66545 | 0.67592 | 0.68583 | 0.69522 | 0.7041 | 0.71248 | 0.72038 | 0.72781 | 0.73481 | 0.74138 | 0.74755 | 0.75333 | 0.75874 | 0.76381 | 0.76854 | 0.77296 | 0.77709 | 0.78093 | 0.78451 | 0.78785 | 0.79095 | 0.79383 | 0.79651 | 0.79899 | 0.8013 | 0.80343 | 0.80541 | 0.80724 | 0.80894 | 0.81051 | 0.81196 | 0.81329 | 0.81453 | 0.81567 | 0.81673 | 0.8177 | 0.81859 | 0.81942 | 0.82018 | 0.82088 | 0.82153 | 0.82212 | 0.82267 | 0.82317 | 0.82363 | 0.82406 | 0.82445 | 0.8248 | 0.82513 | 0.82544 | 0.82571 | 0.82597 | 0.8262 | 0.82642 | 0.82661 | 0.82679
| 85 | 134.9873 | 0.0099941 | 0.013215 | 0.017142 | 0.02185 | 0.027406 | 0.033868 | 0.041285 | 0.049693 | 0.059117 | 0.069568 | 0.081043 | 0.093527 | 0.10699 | 0.1214 | 0.1367 | 0.15284 | 0.16974 | 0.18734 | 0.20554 | 0.22428 | 0.24345 | 0.26299 | 0.28279 | 0.30278 | 0.32287 | 0.34297 | 0.36302 | 0.38294 | 0.40266 | 0.42213 | 0.44127 | 0.46005 | 0.47842 | 0.49633 | 0.51375 | 0.53066 | 0.54702 | 0.56283 | 0.57806 | 0.59271 | 0.60677 | 0.62024 | 0.63312 | 0.64541 | 0.65712 | 0.66826 | 0.67884 | 0.68887 | 0.69837 | 0.70736 | 0.71585 | 0.72385 | 0.73139 | 0.73848 | 0.74515 | 0.75141 | 0.75728 | 0.76278 | 0.76793 | 0.77274 | 0.77724 | 0.78144 | 0.78535 | 0.789 | 0.7924 | 0.79556 | 0.7985 | 0.80123 | 0.80376 | 0.80612 | 0.8083 | 0.81032 | 0.81219 | 0.81393 | 0.81553 | 0.81702 | 0.81839 | 0.81966 | 0.82083 | 0.82191 | 0.82291 | 0.82382 | 0.82467 | 0.82545 | 0.82617 | 0.82684 | 0.82745 | 0.82801 | 0.82853 | 0.829 | 0.82944 | 0.82984 | 0.83021 | 0.83055 | 0.83086 | 0.83115 | 0.83141 | 0.83166 | 0.83188 | 0.83208 | 0.83227
| 86 | 136.1296 | 0.0099947 | 0.013216 | 0.017144 | 0.021853 | 0.02741 | 0.033874 | 0.041293 | 0.049705 | 0.059133 | 0.06959 | 0.081073 | 0.093567 | 0.10705 | 0.12147 | 0.13679 | 0.15295 | 0.16987 | 0.1875 | 0.20574 | 0.22451 | 0.24373 | 0.26331 | 0.28317 | 0.30322 | 0.32337 | 0.34355 | 0.36367 | 0.38367 | 0.40348 | 0.42303 | 0.44227 | 0.46115 | 0.47961 | 0.49763 | 0.51516 | 0.53218 | 0.54866 | 0.56458 | 0.57993 | 0.5947 | 0.60888 | 0.62246 | 0.63546 | 0.64786 | 0.65969 | 0.67095 | 0.68164 | 0.69179 | 0.7014 | 0.71049 | 0.71908 | 0.72719 | 0.73483 | 0.74202 | 0.74878 | 0.75513 | 0.76109 | 0.76667 | 0.7719 | 0.77679 | 0.78136 | 0.78563 | 0.78962 | 0.79333 | 0.79679 | 0.80001 | 0.80301 | 0.80579 | 0.80838 | 0.81078 | 0.813 | 0.81507 | 0.81698 | 0.81876 | 0.8204 | 0.82192 | 0.82332 | 0.82462 | 0.82582 | 0.82692 | 0.82795 | 0.82889 | 0.82976 | 0.83056 | 0.8313 | 0.83198 | 0.83261 | 0.83319 | 0.83372 | 0.83421 | 0.83466 | 0.83507 | 0.83545 | 0.83581 | 0.83613 | 0.83642 | 0.83669 | 0.83694 | 0.83717 | 0.83738 | 0.83758
| 87 | 137.2719 | 0.0099952 | 0.013217 | 0.017145 | 0.021855 | 0.027413 | 0.033879 | 0.041301 | 0.049716 | 0.059148 | 0.06961 | 0.0811 | 0.093604 | 0.10709 | 0.12153 | 0.13687 | 0.15305 | 0.17 | 0.18765 | 0.20592 | 0.22473 | 0.24399 | 0.26362 | 0.28353 | 0.30363 | 0.32384 | 0.34408 | 0.36428 | 0.38436 | 0.40424 | 0.42388 | 0.44321 | 0.46218 | 0.48075 | 0.49887 | 0.5165 | 0.53363 | 0.55022 | 0.56625 | 0.58171 | 0.59659 | 0.61088 | 0.62458 | 0.63769 | 0.65021 | 0.66215 | 0.67352 | 0.68432 | 0.69458 | 0.7043 | 0.71349 | 0.72219 | 0.73039 | 0.73813 | 0.74542 | 0.75227 | 0.75871 | 0.76475 | 0.77042 | 0.77573 | 0.78069 | 0.78534 | 0.78968 | 0.79373 | 0.79751 | 0.80103 | 0.80431 | 0.80736 | 0.81019 | 0.81283 | 0.81528 | 0.81755 | 0.81966 | 0.82162 | 0.82343 | 0.8251 | 0.82666 | 0.82809 | 0.82942 | 0.83065 | 0.83178 | 0.83283 | 0.8338 | 0.83469 | 0.83551 | 0.83627 | 0.83697 | 0.83761 | 0.83821 | 0.83875 | 0.83926 | 0.83972 | 0.84015 | 0.84054 | 0.8409 | 0.84123 | 0.84153 | 0.84181 | 0.84207 | 0.84231 | 0.84252 | 0.84272
| 88 | 138.4142 | 0.0099956 | 0.013217 | 0.017146 | 0.021857 | 0.027416 | 0.033883 | 0.041307 | 0.049725 | 0.059162 | 0.069629 | 0.081126 | 0.093638 | 0.10714 | 0.12159 | 0.13694 | 0.15314 | 0.17011 | 0.18779 | 0.20609 | 0.22493 | 0.24423 | 0.2639 | 0.28386 | 0.30402 | 0.32429 | 0.34459 | 0.36486 | 0.385 | 0.40497 | 0.42469 | 0.44411 | 0.46317 | 0.48182 | 0.50004 | 0.51777 | 0.535 | 0.5517 | 0.56783 | 0.5834 | 0.59839 | 0.6128 | 0.62661 | 0.63983 | 0.65246 | 0.66451 | 0.67598 | 0.68689 | 0.69725 | 0.70707 | 0.71637 | 0.72517 | 0.73347 | 0.7413 | 0.74868 | 0.75562 | 0.76215 | 0.76828 | 0.77402 | 0.77941 | 0.78445 | 0.78917 | 0.79358 | 0.79769 | 0.80154 | 0.80512 | 0.80845 | 0.81156 | 0.81445 | 0.81713 | 0.81963 | 0.82195 | 0.8241 | 0.82609 | 0.82794 | 0.82965 | 0.83124 | 0.83271 | 0.83407 | 0.83532 | 0.83648 | 0.83755 | 0.83854 | 0.83946 | 0.8403 | 0.84108 | 0.8418 | 0.84246 | 0.84307 | 0.84363 | 0.84415 | 0.84462 | 0.84506 | 0.84546 | 0.84583 | 0.84617 | 0.84649 | 0.84678 | 0.84704 | 0.84729 | 0.84751 | 0.84772
| 89 | 139.5565 | 0.009996 | 0.013218 | 0.017148 | 0.021859 | 0.027419 | 0.033888 | 0.041314 | 0.049734 | 0.059175 | 0.069647 | 0.08115 | 0.09367 | 0.10718 | 0.12164 | 0.13701 | 0.15322 | 0.17022 | 0.18792 | 0.20625 | 0.22512 | 0.24446 | 0.26417 | 0.28417 | 0.30438 | 0.32471 | 0.34507 | 0.3654 | 0.38562 | 0.40565 | 0.42545 | 0.44495 | 0.4641 | 0.48284 | 0.50115 | 0.51898 | 0.53631 | 0.5531 | 0.56934 | 0.58502 | 0.60011 | 0.61462 | 0.62854 | 0.64186 | 0.6546 | 0.66676 | 0.67834 | 0.68935 | 0.69981 | 0.70974 | 0.71914 | 0.72803 | 0.73642 | 0.74435 | 0.75182 | 0.75885 | 0.76546 | 0.77167 | 0.77749 | 0.78295 | 0.78807 | 0.79286 | 0.79733 | 0.80152 | 0.80542 | 0.80906 | 0.81245 | 0.81561 | 0.81855 | 0.82129 | 0.82383 | 0.82619 | 0.82838 | 0.83042 | 0.8323 | 0.83405 | 0.83567 | 0.83717 | 0.83856 | 0.83984 | 0.84103 | 0.84213 | 0.84314 | 0.84407 | 0.84494 | 0.84574 | 0.84647 | 0.84715 | 0.84777 | 0.84835 | 0.84888 | 0.84937 | 0.84982 | 0.85023 | 0.85062 | 0.85097 | 0.85129 | 0.85159 | 0.85186 | 0.85211 | 0.85234 | 0.85255
| 90 | 140.6988 | 0.0099964 | 0.013219 | 0.017149 | 0.02186 | 0.027422 | 0.033892 | 0.041319 | 0.049743 | 0.059186 | 0.069663 | 0.081172 | 0.093699 | 0.10722 | 0.12169 | 0.13707 | 0.1533 | 0.17032 | 0.18804 | 0.2064 | 0.2253 | 0.24467 | 0.26442 | 0.28447 | 0.30472 | 0.3251 | 0.34552 | 0.36591 | 0.38619 | 0.4063 | 0.42617 | 0.44575 | 0.46498 | 0.48381 | 0.50221 | 0.52013 | 0.53755 | 0.55444 | 0.57078 | 0.58656 | 0.60175 | 0.61636 | 0.63038 | 0.64381 | 0.65665 | 0.66891 | 0.68059 | 0.69171 | 0.70227 | 0.71229 | 0.72178 | 0.73077 | 0.73926 | 0.74727 | 0.75483 | 0.76194 | 0.76863 | 0.77492 | 0.78083 | 0.78637 | 0.79155 | 0.79641 | 0.80095 | 0.8052 | 0.80916 | 0.81286 | 0.81631 | 0.81952 | 0.82251 | 0.8253 | 0.82789 | 0.83029 | 0.83252 | 0.8346 | 0.83652 | 0.8383 | 0.83996 | 0.84149 | 0.8429 | 0.84421 | 0.84543 | 0.84655 | 0.84759 | 0.84854 | 0.84943 | 0.85024 | 0.851 | 0.85169 | 0.85233 | 0.85292 | 0.85347 | 0.85397 | 0.85443 | 0.85486 | 0.85525 | 0.85561 | 0.85594 | 0.85625 | 0.85653 | 0.85679 | 0.85702 | 0.85724
| 91 | 141.8411 | 0.0099967 | 0.013219 | 0.01715 | 0.021862 | 0.027424 | 0.033895 | 0.041325 | 0.04975 | 0.059197 | 0.069678 | 0.081192 | 0.093726 | 0.10725 | 0.12174 | 0.13713 | 0.15338 | 0.17041 | 0.18815 | 0.20653 | 0.22547 | 0.24487 | 0.26466 | 0.28475 | 0.30504 | 0.32547 | 0.34594 | 0.36639 | 0.38674 | 0.40691 | 0.42685 | 0.4465 | 0.46581 | 0.48473 | 0.50321 | 0.52122 | 0.53873 | 0.55571 | 0.57215 | 0.58802 | 0.60331 | 0.61802 | 0.63214 | 0.64567 | 0.65861 | 0.67096 | 0.68274 | 0.69396 | 0.70462 | 0.71473 | 0.72432 | 0.7334 | 0.74198 | 0.75008 | 0.75772 | 0.76492 | 0.77169 | 0.77806 | 0.78404 | 0.78965 | 0.79491 | 0.79983 | 0.80444 | 0.80875 | 0.81277 | 0.81653 | 0.82003 | 0.82329 | 0.82634 | 0.82917 | 0.8318 | 0.83425 | 0.83652 | 0.83863 | 0.84059 | 0.84241 | 0.8441 | 0.84566 | 0.8471 | 0.84844 | 0.84968 | 0.85083 | 0.85189 | 0.85287 | 0.85377 | 0.85461 | 0.85538 | 0.85609 | 0.85674 | 0.85735 | 0.85791 | 0.85842 | 0.8589 | 0.85933 | 0.85974 | 0.86011 | 0.86045 | 0.86076 | 0.86105 | 0.86132 | 0.86156 | 0.86179
| 92 | 142.9834 | 0.009997 | 0.01322 | 0.01715 | 0.021863 | 0.027426 | 0.033898 | 0.041329 | 0.049757 | 0.059207 | 0.069692 | 0.081211 | 0.093751 | 0.10729 | 0.12178 | 0.13719 | 0.15345 | 0.1705 | 0.18826 | 0.20666 | 0.22563 | 0.24506 | 0.26488 | 0.285 | 0.30534 | 0.32582 | 0.34634 | 0.36685 | 0.38725 | 0.40749 | 0.4275 | 0.44722 | 0.4666 | 0.48559 | 0.50416 | 0.52225 | 0.53985 | 0.55692 | 0.57345 | 0.58941 | 0.6048 | 0.6196 | 0.63382 | 0.64744 | 0.66048 | 0.67293 | 0.6848 | 0.69611 | 0.70686 | 0.71707 | 0.72675 | 0.73591 | 0.74458 | 0.75277 | 0.76049 | 0.76777 | 0.77462 | 0.78107 | 0.78712 | 0.7928 | 0.79813 | 0.80312 | 0.80779 | 0.81216 | 0.81624 | 0.82006 | 0.82361 | 0.82693 | 0.83002 | 0.8329 | 0.83558 | 0.83807 | 0.84038 | 0.84253 | 0.84453 | 0.84638 | 0.8481 | 0.84969 | 0.85116 | 0.85253 | 0.85379 | 0.85496 | 0.85605 | 0.85705 | 0.85797 | 0.85883 | 0.85961 | 0.86034 | 0.86101 | 0.86163 | 0.86221 | 0.86273 | 0.86322 | 0.86367 | 0.86408 | 0.86446 | 0.86481 | 0.86513 | 0.86543 | 0.8657 | 0.86596 | 0.86619
| 93 | 144.1257 | 0.0099973 | 0.01322 | 0.017151 | 0.021865 | 0.027428 | 0.033901 | 0.041334 | 0.049764 | 0.059216 | 0.069704 | 0.081228 | 0.093775 | 0.10732 | 0.12182 | 0.13724 | 0.15351 | 0.17058 | 0.18836 | 0.20679 | 0.22577 | 0.24523 | 0.26509 | 0.28525 | 0.30563 | 0.32615 | 0.34672 | 0.36727 | 0.38773 | 0.40803 | 0.42811 | 0.4479 | 0.46735 | 0.48642 | 0.50506 | 0.52323 | 0.54091 | 0.55807 | 0.57468 | 0.59074 | 0.60621 | 0.62111 | 0.63541 | 0.64913 | 0.66226 | 0.6748 | 0.68677 | 0.69817 | 0.70901 | 0.71931 | 0.72908 | 0.73833 | 0.74708 | 0.75535 | 0.76315 | 0.77051 | 0.77744 | 0.78396 | 0.79009 | 0.79584 | 0.80123 | 0.80629 | 0.81102 | 0.81545 | 0.81959 | 0.82346 | 0.82707 | 0.83044 | 0.83358 | 0.8365 | 0.83922 | 0.84175 | 0.84411 | 0.84629 | 0.84833 | 0.85021 | 0.85196 | 0.85358 | 0.85509 | 0.85648 | 0.85777 | 0.85896 | 0.86007 | 0.86109 | 0.86203 | 0.86291 | 0.86371 | 0.86446 | 0.86515 | 0.86578 | 0.86637 | 0.86691 | 0.86741 | 0.86786 | 0.86829 | 0.86868 | 0.86904 | 0.86937 | 0.86967 | 0.86995 | 0.87021 | 0.87045
| 94 | 145.2681 | 0.0099975 | 0.013221 | 0.017152 | 0.021866 | 0.02743 | 0.033904 | 0.041338 | 0.049769 | 0.059225 | 0.069716 | 0.081244 | 0.093796 | 0.10735 | 0.12186 | 0.13729 | 0.15357 | 0.17065 | 0.18845 | 0.2069 | 0.22591 | 0.2454 | 0.26528 | 0.28548 | 0.30589 | 0.32645 | 0.34707 | 0.36768 | 0.38819 | 0.40855 | 0.42868 | 0.44853 | 0.46806 | 0.48719 | 0.50591 | 0.52416 | 0.54192 | 0.55916 | 0.57586 | 0.592 | 0.60756 | 0.62254 | 0.63694 | 0.65074 | 0.66396 | 0.67659 | 0.68865 | 0.70014 | 0.71107 | 0.72145 | 0.7313 | 0.74064 | 0.74947 | 0.75782 | 0.76571 | 0.77314 | 0.78015 | 0.78674 | 0.79293 | 0.79875 | 0.80422 | 0.80933 | 0.81413 | 0.81862 | 0.82281 | 0.82674 | 0.8304 | 0.83382 | 0.837 | 0.83997 | 0.84274 | 0.84531 | 0.8477 | 0.84993 | 0.85199 | 0.85391 | 0.85569 | 0.85734 | 0.85888 | 0.8603 | 0.86161 | 0.86283 | 0.86396 | 0.865 | 0.86596 | 0.86686 | 0.86768 | 0.86844 | 0.86914 | 0.86979 | 0.87039 | 0.87094 | 0.87146 | 0.87193 | 0.87236 | 0.87276 | 0.87313 | 0.87347 | 0.87378 | 0.87407 | 0.87433 | 0.87458
| 95 | 146.4104 | 0.0099977 | 0.013221 | 0.017153 | 0.021867 | 0.027432 | 0.033907 | 0.041342 | 0.049775 | 0.059232 | 0.069727 | 0.081259 | 0.093816 | 0.10737 | 0.12189 | 0.13733 | 0.15363 | 0.17072 | 0.18854 | 0.207 | 0.22604 | 0.24555 | 0.26546 | 0.28569 | 0.30614 | 0.32674 | 0.34741 | 0.36806 | 0.38862 | 0.40903 | 0.42922 | 0.44914 | 0.46872 | 0.48793 | 0.50672 | 0.52504 | 0.54288 | 0.5602 | 0.57697 | 0.59319 | 0.60884 | 0.62391 | 0.63839 | 0.65228 | 0.66558 | 0.6783 | 0.69045 | 0.70202 | 0.71303 | 0.7235 | 0.73344 | 0.74285 | 0.75177 | 0.7602 | 0.76816 | 0.77567 | 0.78274 | 0.78941 | 0.79567 | 0.80156 | 0.80708 | 0.81226 | 0.81712 | 0.82167 | 0.82592 | 0.82989 | 0.83361 | 0.83707 | 0.8403 | 0.84332 | 0.84612 | 0.84874 | 0.85117 | 0.85343 | 0.85553 | 0.85748 | 0.8593 | 0.86098 | 0.86254 | 0.86398 | 0.86532 | 0.86656 | 0.86771 | 0.86878 | 0.86976 | 0.87067 | 0.87151 | 0.87229 | 0.87301 | 0.87367 | 0.87429 | 0.87485 | 0.87537 | 0.87586 | 0.8763 | 0.87671 | 0.87709 | 0.87743 | 0.87775 | 0.87805 | 0.87832 | 0.87857
| 96 | 147.5527 | 0.009998 | 0.013221 | 0.017153 | 0.021868 | 0.027433 | 0.033909 | 0.041345 | 0.04978 | 0.059239 | 0.069737 | 0.081273 | 0.093834 | 0.1074 | 0.12193 | 0.13737 | 0.15368 | 0.17079 | 0.18862 | 0.2071 | 0.22616 | 0.2457 | 0.26564 | 0.28589 | 0.30638 | 0.32701 | 0.34772 | 0.36841 | 0.38903 | 0.40949 | 0.42974 | 0.44971 | 0.46936 | 0.48863 | 0.50748 | 0.52588 | 0.54379 | 0.56118 | 0.57804 | 0.59433 | 0.61006 | 0.62521 | 0.63977 | 0.65375 | 0.66713 | 0.67994 | 0.69216 | 0.70382 | 0.71491 | 0.72546 | 0.73548 | 0.74497 | 0.75397 | 0.76247 | 0.77051 | 0.77809 | 0.78524 | 0.79197 | 0.7983 | 0.80425 | 0.80984 | 0.81508 | 0.82 | 0.8246 | 0.8289 | 0.83293 | 0.83669 | 0.84021 | 0.84349 | 0.84654 | 0.84939 | 0.85204 | 0.85451 | 0.85681 | 0.85895 | 0.86093 | 0.86277 | 0.86449 | 0.86607 | 0.86754 | 0.86891 | 0.87017 | 0.87134 | 0.87243 | 0.87343 | 0.87436 | 0.87522 | 0.87601 | 0.87675 | 0.87743 | 0.87805 | 0.87863 | 0.87916 | 0.87966 | 0.88011 | 0.88053 | 0.88092 | 0.88127 | 0.8816 | 0.8819 | 0.88218 | 0.88244
| 97 | 148.695 | 0.0099981 | 0.013222 | 0.017154 | 0.021869 | 0.027434 | 0.033911 | 0.041348 | 0.049785 | 0.059246 | 0.069746 | 0.081285 | 0.093851 | 0.10742 | 0.12195 | 0.13741 | 0.15373 | 0.17085 | 0.18869 | 0.2072 | 0.22627 | 0.24583 | 0.26579 | 0.28608 | 0.3066 | 0.32727 | 0.34801 | 0.36875 | 0.38941 | 0.40992 | 0.43022 | 0.45025 | 0.46996 | 0.48929 | 0.50821 | 0.52667 | 0.54465 | 0.56211 | 0.57904 | 0.59542 | 0.61122 | 0.62645 | 0.64109 | 0.65514 | 0.66861 | 0.68149 | 0.6938 | 0.70554 | 0.71671 | 0.72734 | 0.73743 | 0.747 | 0.75607 | 0.76465 | 0.77276 | 0.78041 | 0.78763 | 0.79443 | 0.80082 | 0.80684 | 0.81249 | 0.81779 | 0.82276 | 0.82742 | 0.83178 | 0.83586 | 0.83967 | 0.84323 | 0.84655 | 0.84965 | 0.85254 | 0.85523 | 0.85774 | 0.86007 | 0.86224 | 0.86426 | 0.86613 | 0.86787 | 0.86949 | 0.87098 | 0.87237 | 0.87366 | 0.87485 | 0.87596 | 0.87698 | 0.87793 | 0.8788 | 0.87961 | 0.88036 | 0.88105 | 0.88169 | 0.88228 | 0.88283 | 0.88333 | 0.8838 | 0.88423 | 0.88462 | 0.88499 | 0.88532 | 0.88563 | 0.88592 | 0.88618
| 98 | 149.8373 | 0.0099983 | 0.013222 | 0.017154 | 0.021869 | 0.027436 | 0.033913 | 0.041351 | 0.049789 | 0.059252 | 0.069754 | 0.081297 | 0.093867 | 0.10744 | 0.12198 | 0.13744 | 0.15377 | 0.1709 | 0.18876 | 0.20728 | 0.22637 | 0.24595 | 0.26594 | 0.28626 | 0.30681 | 0.32751 | 0.34829 | 0.36907 | 0.38977 | 0.41033 | 0.43068 | 0.45076 | 0.47052 | 0.48991 | 0.50889 | 0.52742 | 0.54547 | 0.563 | 0.58 | 0.59645 | 0.61233 | 0.62763 | 0.64234 | 0.65648 | 0.67002 | 0.68298 | 0.69536 | 0.70718 | 0.71843 | 0.72913 | 0.7393 | 0.74895 | 0.75809 | 0.76674 | 0.77492 | 0.78264 | 0.78992 | 0.79679 | 0.80325 | 0.80932 | 0.81503 | 0.82039 | 0.82542 | 0.83013 | 0.83454 | 0.83867 | 0.84253 | 0.84614 | 0.8495 | 0.85265 | 0.85558 | 0.85831 | 0.86085 | 0.86322 | 0.86542 | 0.86747 | 0.86937 | 0.87114 | 0.87278 | 0.8743 | 0.87572 | 0.87703 | 0.87824 | 0.87937 | 0.88041 | 0.88137 | 0.88227 | 0.88309 | 0.88386 | 0.88456 | 0.88521 | 0.88582 | 0.88638 | 0.88689 | 0.88737 | 0.8878 | 0.88821 | 0.88858 | 0.88893 | 0.88924 | 0.88954 | 0.88981
| 99 | 150.9796 | 0.0099985 | 0.013222 | 0.017155 | 0.02187 | 0.027437 | 0.033915 | 0.041354 | 0.049793 | 0.059258 | 0.069762 | 0.081308 | 0.093882 | 0.10746 | 0.12201 | 0.13748 | 0.15382 | 0.17096 | 0.18883 | 0.20736 | 0.22647 | 0.24607 | 0.26608 | 0.28642 | 0.307 | 0.32774 | 0.34855 | 0.36936 | 0.39011 | 0.41071 | 0.43111 | 0.45124 | 0.47106 | 0.4905 | 0.50954 | 0.52813 | 0.54624 | 0.56384 | 0.58091 | 0.59742 | 0.61337 | 0.62875 | 0.64354 | 0.65774 | 0.67136 | 0.6844 | 0.69686 | 0.70874 | 0.72007 | 0.73085 | 0.74109 | 0.75081 | 0.76002 | 0.76874 | 0.77699 | 0.78477 | 0.79212 | 0.79905 | 0.80557 | 0.81171 | 0.81748 | 0.82289 | 0.82797 | 0.83274 | 0.8372 | 0.84138 | 0.84528 | 0.84894 | 0.85235 | 0.85553 | 0.8585 | 0.86127 | 0.86385 | 0.86625 | 0.86848 | 0.87056 | 0.87249 | 0.87429 | 0.87596 | 0.87751 | 0.87894 | 0.88028 | 0.88151 | 0.88266 | 0.88372 | 0.8847 | 0.88561 | 0.88645 | 0.88723 | 0.88795 | 0.88862 | 0.88923 | 0.8898 | 0.89033 | 0.89081 | 0.89126 | 0.89168 | 0.89206 | 0.89241 | 0.89273 | 0.89303 | 0.89331
| 100 | 152.1219 | 0.0099986 | 0.013223 | 0.017155 | 0.021871 | 0.027438 | 0.033916 | 0.041356 | 0.049796 | 0.059263 | 0.06977 | 0.081318 | 0.093895 | 0.10748 | 0.12203 | 0.13751 | 0.15385 | 0.17101 | 0.18889 | 0.20744 | 0.22656 | 0.24618 | 0.26622 | 0.28658 | 0.30718 | 0.32795 | 0.34879 | 0.36964 | 0.39043 | 0.41107 | 0.43151 | 0.45169 | 0.47156 | 0.49106 | 0.51016 | 0.52881 | 0.54698 | 0.56464 | 0.58177 | 0.59835 | 0.61437 | 0.62982 | 0.64468 | 0.65895 | 0.67264 | 0.68575 | 0.69828 | 0.71024 | 0.72164 | 0.73249 | 0.7428 | 0.75259 | 0.76187 | 0.77065 | 0.77897 | 0.78682 | 0.79423 | 0.80122 | 0.80781 | 0.814 | 0.81982 | 0.8253 | 0.83043 | 0.83525 | 0.83976 | 0.84398 | 0.84793 | 0.85163 | 0.85508 | 0.85831 | 0.86132 | 0.86412 | 0.86674 | 0.86917 | 0.87144 | 0.87355 | 0.87551 | 0.87733 | 0.87903 | 0.8806 | 0.88206 | 0.88342 | 0.88467 | 0.88584 | 0.88692 | 0.88792 | 0.88884 | 0.8897 | 0.89049 | 0.89123 | 0.89191 | 0.89254 | 0.89312 | 0.89365 | 0.89415 | 0.89461 | 0.89503 | 0.89542 | 0.89578 | 0.89611 | 0.89642 | 0.8967
Calc. Joint Conf. Values

## Iso-curves
| FY08$M | Months | [12 empty] | FY08$M | Months
| Cost | Sched | Cost | Sched | Cost | Sched | Cost | Sched | Cost | Sched | Cost | Sched | Cost | Sched | Cost | Sched | Cost | Sched | Cost | Sched
Conf Level | 0.1 |  | 0.2 |  | 0.3 |  | 0.4 |  | 0.5 |  | 0.6 |  | 0.65 |  | 0.7 |  | 0.8 |  | 0.9
| 56.1684 | 44.3611 | 67.5914 | 40.9638 | 75.5875 | 53.9867 | 84.726 | 48.3246 | 92.7221 | 57.384 | 103.0028 | 54.553 | 107.572 | 61.9138 | 113.2836 | 67.0097 | 128.1335 | 68.1422 | 152.1219 | 69.8408
| 56.1684 | 44.9273 | 67.5914 | 41.53 | 75.5875 | 54.553 | 84.726 | 48.8908 | 92.7221 | 57.9503 | 103.0028 | 55.1192 | 107.572 | 62.48 | 113.2836 | 67.5759 | 128.1335 | 68.7084 | 152.1219 | 70.407
| 56.1684 | 45.4935 | 67.5914 | 42.0962 | 75.5875 | 55.1192 | 84.726 | 49.457 | 92.7221 | 58.5165 | 103.0028 | 55.6854 | 107.572 | 63.0462 | 113.2836 | 68.1422 | 128.1335 | 69.2746 | 152.1219 | 70.9732
| 56.1684 | 46.0597 | 67.5914 | 42.6624 | 75.5875 | 55.6854 | 84.726 | 50.0232 | 92.7221 | 59.0827 | 103.0028 | 56.2516 | 107.572 | 63.6124 | 113.2836 | 68.7084 | 128.1335 | 69.8408 | 152.1219 | 71.5394
| 56.1684 | 46.6259 | 67.5914 | 43.2286 | 75.5875 | 56.2516 | 84.726 | 50.5894 | 92.7221 | 59.6489 | 103.0028 | 56.8178 | 107.572 | 64.1786 | 113.2836 | 69.2746 | 128.1335 | 70.407 | 152.1219 | 72.1057
| 56.1684 | 47.1921 | 67.5914 | 43.7948 | 75.5875 | 56.8178 | 84.726 | 51.1557 | 92.7221 | 60.2151 | 103.0028 | 57.384 | 107.572 | 64.7449 | 113.2836 | 69.8408 | 128.1335 | 70.9732 | 152.1219 | 72.6719
| 56.1684 | 47.7584 | 67.5914 | 44.3611 | 75.5875 | 57.384 | 84.726 | 51.7219 | 92.7221 | 60.7813 | 103.0028 | 57.9503 | 107.572 | 65.3111 | 113.2836 | 70.407 | 128.1335 | 71.5394
| 56.1684 | 48.3246 | 67.5914 | 44.9273 | 75.5875 | 57.9503 | 84.726 | 52.2881 | 92.7221 | 61.3476 | 103.0028 | 58.5165 | 107.572 | 65.8773 | 113.2836 | 70.9732 | 128.1335 | 72.1057
| 56.1684 | 48.8908 | 67.5914 | 45.4935 | 75.5875 | 58.5165 | 84.726 | 52.8543 | 92.7221 | 61.9138 | 103.0028 | 59.0827 | 107.572 | 66.4435 | 113.2836 | 71.5394 | 128.1335 | 72.6719
| 56.1684 | 49.457 | 67.5914 | 46.0597 | 75.5875 | 59.0827 | 84.726 | 53.4205 | 92.7221 | 62.48 | 103.0028 | 59.6489 | 107.572 | 67.0097 | 113.2836 | 72.1057 | 129.2758 | 61.3476
| 56.1684 | 50.0232 | 67.5914 | 46.6259 | 75.5875 | 59.6489 | 84.726 | 53.9867 | 92.7221 | 63.0462 | 103.0028 | 60.2151 | 107.572 | 67.5759 | 113.2836 | 72.6719 | 129.2758 | 61.9138
| 56.1684 | 50.5894 | 67.5914 | 47.1921 | 75.5875 | 60.2151 | 84.726 | 54.553 | 92.7221 | 63.6124 | 103.0028 | 60.7813 | 107.572 | 68.1422 | 114.4259 | 57.384 | 129.2758 | 62.48
| 56.1684 | 51.1557 | 67.5914 | 47.7584 | 75.5875 | 60.7813 | 84.726 | 55.1192 | 92.7221 | 64.1786 | 103.0028 | 61.3476 | 107.572 | 68.7084 | 114.4259 | 57.9503 | 129.2758 | 63.0462
| 56.1684 | 51.7219 | 67.5914 | 48.3246 | 75.5875 | 61.3476 | 84.726 | 55.6854 | 92.7221 | 64.7449 | 103.0028 | 61.9138 | 107.572 | 69.2746 | 114.4259 | 58.5165 | 129.2758 | 63.6124
| 56.1684 | 52.2881 | 67.5914 | 48.8908 | 75.5875 | 61.9138 | 84.726 | 56.2516 | 92.7221 | 65.3111 | 103.0028 | 62.48 | 107.572 | 69.8408 | 114.4259 | 59.0827 | 129.2758 | 64.1786
| 56.1684 | 52.8543 | 67.5914 | 49.457 | 75.5875 | 62.48 | 84.726 | 56.8178 | 92.7221 | 65.8773 | 103.0028 | 63.0462 | 107.572 | 70.407 | 114.4259 | 59.6489 | 129.2758 | 64.7449
| 56.1684 | 53.4205 | 67.5914 | 50.0232 | 75.5875 | 63.0462 | 85.8683 | 43.7948 | 92.7221 | 66.4435 | 103.0028 | 63.6124 | 107.572 | 70.9732 | 114.4259 | 60.2151 | 129.2758 | 65.3111
| 56.1684 | 53.9867 | 67.5914 | 50.5894 | 75.5875 | 63.6124 | 85.8683 | 44.3611 | 92.7221 | 67.0097 | 104.1451 | 50.5894 | 107.572 | 71.5394 | 114.4259 | 60.7813 | 129.2758 | 65.8773
| 56.1684 | 54.553 | 67.5914 | 51.1557 | 75.5875 | 64.1786 | 85.8683 | 44.9273 | 92.7221 | 67.5759 | 104.1451 | 51.1557 | 107.572 | 72.1057 | 114.4259 | 61.3476 | 129.2758 | 66.4435
| 56.1684 | 55.1192 | 67.5914 | 51.7219 | 75.5875 | 64.7449 | 85.8683 | 45.4935 | 92.7221 | 68.1422 | 104.1451 | 51.7219 | 107.572 | 72.6719 | 114.4259 | 61.9138 | 129.2758 | 67.0097
| 56.1684 | 55.6854 | 68.7337 | 37.0002 | 75.5875 | 65.3111 | 85.8683 | 46.0597 | 92.7221 | 68.7084 | 104.1451 | 52.2881 | 108.7143 | 54.553 | 114.4259 | 62.48 | 129.2758 | 67.5759
| 56.1684 | 56.2516 | 68.7337 | 37.5665 | 75.5875 | 65.8773 | 87.0106 | 41.53 | 92.7221 | 69.2746 | 104.1451 | 52.8543 | 108.7143 | 55.1192 | 114.4259 | 63.0462 | 129.2758 | 68.1422
| 56.1684 | 56.8178 | 68.7337 | 38.1327 | 75.5875 | 66.4435 | 87.0106 | 42.0962 | 92.7221 | 69.8408 | 105.2874 | 48.3246 | 108.7143 | 55.6854 | 114.4259 | 63.6124 | 129.2758 | 68.7084
| 56.1684 | 57.384 | 68.7337 | 38.6989 | 75.5875 | 67.0097 | 87.0106 | 42.6624 | 92.7221 | 70.407 | 105.2874 | 48.8908 | 108.7143 | 56.2516 | 114.4259 | 64.1786 | 129.2758 | 69.2746
| 56.1684 | 57.9503 | 68.7337 | 39.2651 | 75.5875 | 67.5759 | 88.1529 | 40.3975 | 92.7221 | 70.9732 | 105.2874 | 49.457 | 108.7143 | 56.8178 | 114.4259 | 64.7449 | 129.2758 | 69.8408
| 56.1684 | 58.5165 | 69.876 | 34.7354 | 75.5875 | 68.1422 | 88.1529 | 40.9638 | 92.7221 | 71.5394 | 105.2874 | 50.0232 | 108.7143 | 57.384 | 114.4259 | 65.3111 | 129.2758 | 70.407
| 56.1684 | 59.0827 | 69.876 | 35.3016 | 75.5875 | 68.7084 | 89.2952 | 39.2651 | 92.7221 | 72.1057 | 106.4297 | 46.6259 | 108.7143 | 57.9503 | 114.4259 | 65.8773 | 129.2758 | 70.9732
| 56.1684 | 59.6489 | 69.876 | 35.8678 | 75.5875 | 69.2746 | 89.2952 | 39.8313 | 92.7221 | 72.6719 | 106.4297 | 47.1921 | 108.7143 | 58.5165 | 114.4259 | 66.4435 | 129.2758 | 71.5394
| 56.1684 | 60.2151 | 71.0183 | 33.6029 | 75.5875 | 69.8408 | 90.4375 | 38.1327 | 93.8644 | 49.457 | 106.4297 | 47.7584 | 108.7143 | 59.0827 | 114.4259 | 67.0097 | 129.2758 | 72.1057
| 56.1684 | 60.7813 | 71.0183 | 34.1692 | 75.5875 | 70.407 | 90.4375 | 38.6989 | 93.8644 | 50.0232 | 107.572 | 45.4935 | 108.7143 | 59.6489 | 115.5682 | 53.9867 | 129.2758 | 72.6719
| 56.1684 | 61.3476 | 72.1606 | 32.4705 | 75.5875 | 70.9732 | 91.5798 | 37.5665 | 93.8644 | 50.5894 | 107.572 | 46.0597 | 108.7143 | 60.2151 | 115.5682 | 54.553 | 130.4181 | 58.5165
| 56.1684 | 61.9138 | 72.1606 | 33.0367 | 75.5875 | 71.5394 | 92.7221 | 37.0002 | 93.8644 | 51.1557 | 108.7143 | 44.9273 | 109.8566 | 51.7219 | 115.5682 | 55.1192 | 130.4181 | 59.0827
| 56.1684 | 62.48 | 73.3029 | 31.9043 | 75.5875 | 72.1057 | 93.8644 | 36.434 | 93.8644 | 51.7219 | 109.8566 | 43.7948 | 109.8566 | 52.2881 | 115.5682 | 55.6854 | 130.4181 | 59.6489
| 56.1684 | 63.0462 | 74.4452 | 31.3381 | 75.5875 | 72.6719 | 95.0067 | 35.8678 | 93.8644 | 52.2881 | 109.8566 | 44.3611 | 109.8566 | 52.8543 | 115.5682 | 56.2516 | 130.4181 | 60.2151
| 56.1684 | 63.6124 | 75.5875 | 30.7719 | 76.7298 | 43.2286 | 97.2913 | 35.3016 | 93.8644 | 52.8543 | 110.9989 | 43.2286 | 109.8566 | 53.4205 | 115.5682 | 56.8178 | 130.4181 | 60.7813
| 56.1684 | 64.1786 | 76.7298 | 30.2056 | 76.7298 | 43.7948 | 98.4336 | 34.7354 | 93.8644 | 53.4205 | 112.1412 | 42.6624 | 109.8566 | 53.9867 | 115.5682 | 57.384 | 130.4181 | 61.3476
| 56.1684 | 64.7449 | 77.8721 | 29.6394 | 76.7298 | 44.3611 | 99.5759 | 34.7354 | 95.0067 | 46.0597 | 113.2836 | 42.0962 | 110.9989 | 49.457 | 116.7105 | 51.7219 | 130.4181 | 61.9138
| 56.1684 | 65.3111 | 79.0144 | 29.6394 | 76.7298 | 44.9273 | 101.8605 | 34.1692 | 95.0067 | 46.6259 | 114.4259 | 42.0962 | 110.9989 | 50.0232 | 116.7105 | 52.2881 | 130.4181 | 62.48
| 56.1684 | 65.8773 | 80.1567 | 29.0732 | 76.7298 | 45.4935 | 104.1451 | 33.6029 | 95.0067 | 47.1921 | 115.5682 | 41.53 | 110.9989 | 50.5894 | 116.7105 | 52.8543 | 130.4181 | 63.0462
| 56.1684 | 66.4435 | 82.4414 | 28.507 | 76.7298 | 46.0597 | 105.2874 | 33.6029 | 95.0067 | 47.7584 | 116.7105 | 40.9638 | 110.9989 | 51.1557 | 116.7105 | 53.4205 | 130.4181 | 63.6124
| 56.1684 | 67.0097 | 83.5837 | 28.507 | 76.7298 | 46.6259 | 106.4297 | 33.6029 | 96.149 | 44.3611 | 117.8528 | 40.9638 | 112.1412 | 48.3246 | 116.7105 | 53.9867 | 131.5604 | 56.2516
| 56.1684 | 67.5759 | 84.726 | 27.9408 | 76.7298 | 47.1921 | 108.7143 | 33.0367 | 96.149 | 44.9273 | 118.9951 | 40.3975 | 112.1412 | 48.8908 | 117.8528 | 50.5894 | 131.5604 | 56.8178
| 56.1684 | 68.1422 | 85.8683 | 27.9408 | 77.8721 | 39.8313 | 109.8566 | 33.0367 | 96.149 | 45.4935 | 120.1374 | 40.3975 | 113.2836 | 47.1921 | 117.8528 | 51.1557 | 131.5604 | 57.384
| 56.1684 | 68.7084 | 87.0106 | 27.9408 | 77.8721 | 40.3975 | 110.9989 | 33.0367 | 97.2913 | 42.6624 | 121.2797 | 39.8313 | 113.2836 | 47.7584 | 117.8528 | 51.7219 | 131.5604 | 57.9503
| 56.1684 | 69.2746 | 89.2952 | 27.3746 | 77.8721 | 40.9638 | 115.5682 | 32.4705 | 97.2913 | 43.2286 | 122.422 | 39.8313 | 114.4259 | 46.0597 | 118.9951 | 49.457 | 131.5604 | 58.5165
| 56.1684 | 69.8408 | 90.4375 | 27.3746 | 77.8721 | 41.53 | 116.7105 | 32.4705 | 97.2913 | 43.7948 | 123.5643 | 39.8313 | 114.4259 | 46.6259 | 118.9951 | 50.0232 | 131.5604 | 59.0827
| 56.1684 | 70.407 | 91.5798 | 27.3746 | 79.0144 | 38.1327 | 117.8528 | 32.4705 | 98.4336 | 42.0962 | 124.7066 | 39.2651 | 115.5682 | 45.4935 | 120.1374 | 48.3246 | 131.5604 | 59.6489
| 56.1684 | 70.9732 | 92.7221 | 27.3746 | 79.0144 | 38.6989 | 118.9951 | 32.4705 | 99.5759 | 40.9638 | 125.8489 | 39.2651 | 115.5682 | 46.0597 | 120.1374 | 48.8908 | 132.7027 | 55.1192
| 56.1684 | 71.5394 | 96.149 | 26.8083 | 80.1567 | 36.434 | 126.9912 | 31.9043 | 99.5759 | 41.53 | 126.9912 | 39.2651 | 116.7105 | 44.9273 | 121.2797 | 47.7584 | 132.7027 | 55.6854
| 56.1684 | 72.1057 | 97.2913 | 26.8083 | 80.1567 | 37.0002 | 128.1335 | 31.9043 | 100.7182 | 40.3975 | 130.4181 | 38.6989 | 117.8528 | 44.3611 | 121.2797 | 48.3246 | 132.7027 | 56.2516
| 56.1684 | 72.6719 | 98.4336 | 26.8083 | 81.2991 | 35.8678 | 129.2758 | 31.9043 | 101.8605 | 39.8313 | 131.5604 | 38.6989 | 118.9951 | 43.7948 | 122.422 | 47.1921 | 132.7027 | 56.8178
| 57.3107 | 34.7354 | 99.5759 | 26.8083 | 82.4414 | 34.7354 | 130.4181 | 31.9043 | 103.0028 | 39.2651 | 132.7027 | 38.6989 | 120.1374 | 43.2286 | 123.5643 | 46.6259 | 132.7027 | 57.384
| 57.3107 | 35.3016 | 100.7182 | 26.8083 | 82.4414 | 35.3016 | 131.5604 | 31.9043 | 104.1451 | 38.6989 | 137.2719 | 38.1327 | 120.1374 | 43.7948 | 124.7066 | 46.0597 | 133.845 | 53.9867
| 57.3107 | 35.8678 | 109.8566 | 26.2421 | 83.5837 | 34.1692 | 132.7027 | 31.9043 | 105.2874 | 38.6989 | 138.4142 | 38.1327 | 121.2797 | 43.2286 | 125.8489 | 45.4935 | 133.845 | 54.553
| 57.3107 | 36.434 | 110.9989 | 26.2421 | 84.726 | 33.6029 | 133.845 | 31.9043 | 106.4297 | 38.1327 | 139.5565 | 38.1327 | 122.422 | 42.6624 | 126.9912 | 44.9273 | 133.845 | 55.1192
| 57.3107 | 37.0002 | 112.1412 | 26.2421 | 85.8683 | 33.0367 | 134.9873 | 31.9043 | 107.572 | 37.5665 | 140.6988 | 38.1327 | 123.5643 | 42.6624 | 126.9912 | 45.4935 | 133.845 | 55.6854
| 57.3107 | 37.5665 | 113.2836 | 26.2421 | 87.0106 | 33.0367 | 136.1296 | 31.9043 | 108.7143 | 37.5665 | 141.8411 | 38.1327 | 124.7066 | 42.0962 | 128.1335 | 44.9273 | 134.9873 | 52.8543
| 57.3107 | 38.1327 | 114.4259 | 26.2421 | 88.1529 | 32.4705 |  |  | 110.9989 | 37.0002 | 148.695 | 37.5665 | 125.8489 | 42.0962 | 129.2758 | 44.3611 | 134.9873 | 53.4205
| 57.3107 | 38.6989 | 115.5682 | 26.2421 | 90.4375 | 31.9043 |  |  | 112.1412 | 37.0002 | 149.8373 | 37.5665 | 126.9912 | 41.53 | 130.4181 | 44.3611 | 134.9873 | 53.9867
| 57.3107 | 39.2651 | 116.7105 | 26.2421 | 92.7221 | 31.3381 |  |  | 113.2836 | 36.434 | 150.9796 | 37.5665 | 128.1335 | 41.53 | 131.5604 | 43.7948 | 134.9873 | 54.553
| 57.3107 | 39.8313 | 117.8528 | 26.2421 | 93.8644 | 31.3381 |  |  | 114.4259 | 36.434 | 152.1219 | 37.5665 | 129.2758 | 41.53 | 132.7027 | 43.7948 | 136.1296 | 52.2881
| 57.3107 | 40.3975 | 118.9951 | 26.2421 | 96.149 | 30.7719 |  |  | 115.5682 | 36.434 |  |  | 130.4181 | 40.9638 | 133.845 | 43.2286 | 136.1296 | 52.8543
| 57.3107 | 40.9638 | 120.1374 | 26.2421 | 97.2913 | 30.7719 |  |  | 117.8528 | 35.8678 |  |  | 131.5604 | 40.9638 | 134.9873 | 43.2286 | 136.1296 | 53.4205
| 57.3107 | 41.53 | 121.2797 | 26.2421 | 100.7182 | 30.2056 |  |  | 118.9951 | 35.8678 |  |  | 132.7027 | 40.9638 | 136.1296 | 43.2286 | 137.2719 | 51.7219
| 57.3107 | 42.0962 | 122.422 | 26.2421 | 101.8605 | 30.2056 |  |  | 120.1374 | 35.8678 |  |  | 134.9873 | 40.3975 | 138.4142 | 42.6624 | 137.2719 | 52.2881
| 57.3107 | 42.6624 | 123.5643 | 26.2421 | 103.0028 | 30.2056 |  |  | 124.7066 | 35.3016 |  |  | 136.1296 | 40.3975 | 139.5565 | 42.6624 | 138.4142 | 51.1557
| 57.3107 | 43.2286 | 124.7066 | 26.2421 | 107.572 | 29.6394 |  |  | 125.8489 | 35.3016 |  |  | 137.2719 | 40.3975 | 140.6988 | 42.6624 | 138.4142 | 51.7219
| 57.3107 | 43.7948 | 125.8489 | 26.2421 | 108.7143 | 29.6394 |  |  | 126.9912 | 35.3016 |  |  | 138.4142 | 40.3975 | 142.9834 | 42.0962 | 139.5565 | 50.5894
| 58.453 | 31.9043 | 126.9912 | 26.2421 | 109.8566 | 29.6394 |  |  | 128.1335 | 35.3016 |  |  | 141.8411 | 39.8313 | 144.1257 | 42.0962 | 139.5565 | 51.1557
| 58.453 | 32.4705 |  |  | 110.9989 | 29.6394 |  |  | 134.9873 | 34.7354 |  |  | 142.9834 | 39.8313 | 145.2681 | 42.0962 | 140.6988 | 50.0232
| 58.453 | 33.0367 |  |  | 112.1412 | 29.6394 |  |  | 136.1296 | 34.7354 |  |  | 144.1257 | 39.8313 | 146.4104 | 42.0962 | 140.6988 | 50.5894
| 58.453 | 33.6029 |  |  | 122.422 | 29.0732 |  |  | 137.2719 | 34.7354 |  |  | 145.2681 | 39.8313 | 147.5527 | 42.0962 | 141.8411 | 50.0232
| 58.453 | 34.1692 |  |  | 123.5643 | 29.0732 |  |  | 138.4142 | 34.7354 |  |  | 146.4104 | 39.8313 | 149.8373 | 41.53 | 142.9834 | 49.457
| 59.5953 | 30.2056 |  |  | 124.7066 | 29.0732 |  |  | 139.5565 | 34.7354 |  |  | 147.5527 | 39.8313 | 150.9796 | 41.53 | 142.9834 | 50.0232
| 59.5953 | 30.7719 |  |  | 125.8489 | 29.0732 |  |  | 140.6988 | 34.7354 |  |  |  |  | 152.1219 | 41.53 | 144.1257 | 48.8908
| 59.5953 | 31.3381 |  |  | 126.9912 | 29.0732 |  |  | 141.8411 | 34.7354 | [6 empty] | 144.1257 | 49.457
| 60.7376 | 29.0732 |  |  | 128.1335 | 29.0732 | [10 empty] | 145.2681 | 48.8908
| 60.7376 | 29.6394 |  |  | 129.2758 | 29.0732 | [10 empty] | 146.4104 | 48.3246
| 60.7376 | 30.2056 |  |  | 130.4181 | 29.0732 | [10 empty] | 146.4104 | 48.8908
| 61.8799 | 27.9408 |  |  | 131.5604 | 29.0732 | [10 empty] | 147.5527 | 48.3246
| 61.8799 | 28.507 |  |  | 132.7027 | 29.0732 | [10 empty] | 148.695 | 48.3246
| 63.0222 | 27.3746 |  |  | 133.845 | 29.0732 | [10 empty] | 149.8373 | 47.7584
| 63.0222 | 27.9408 |  |  | 134.9873 | 29.0732 | [10 empty] | 149.8373 | 48.3246
| 64.1645 | 26.8083 |  |  | 136.1296 | 29.0732 | [10 empty] | 150.9796 | 47.7584
| 64.1645 | 27.3746 |  |  | 137.2719 | 29.0732 | [10 empty] | 152.1219 | 47.7584
| 65.3068 | 26.2421
| 65.3068 | 26.8083
| 66.4491 | 25.6759
| 66.4491 | 26.2421
| 67.5914 | 25.6759
| 68.7337 | 25.1097
| 68.7337 | 25.6759
| 69.876 | 25.1097
| 71.0183 | 24.5435
| 71.0183 | 25.1097
| 72.1606 | 24.5435
| 73.3029 | 24.5435
| 74.4452 | 24.5435
| 75.5875 | 23.9773
| 76.7298 | 23.9773
| 77.8721 | 23.9773
| 79.0144 | 23.9773
| 80.1567 | 23.411
| 81.2991 | 23.411
| 82.4414 | 23.411
| 83.5837 | 23.411
| 84.726 | 23.411
| 85.8683 | 23.411
| 87.0106 | 23.411
| 90.4375 | 22.8448
| 91.5798 | 22.8448
| 92.7221 | 22.8448
| 93.8644 | 22.8448
| 95.0067 | 22.8448
| 96.149 | 22.8448
| 97.2913 | 22.8448
| 98.4336 | 22.8448
| 99.5759 | 22.8448
| 100.7182 | 22.8448
| 101.8605 | 22.8448
| 103.0028 | 22.8448
| 104.1451 | 22.8448
| 105.2874 | 22.8448
| 106.4297 | 22.8448
| 107.572 | 22.8448
| 108.7143 | 22.8448
| 109.8566 | 22.8448

## Conditional Conf
Conditional Probabilites
Project Budget: |  | 80
Project Schedule: |  | 30
Budget Confidence Given Schedule |  | 42.91% | <---confidence level assuming schedule is fixed
Schedule Confidence Given Budget |  | 41.88% | <---confidence level assuming budget is fixed
| Schedule Fixed |  | Cost Fixed |  | Conditional Cost Conf. | Conditional Sched. Conf.
| Mean | Sigma | Mean | Sigma
Bivariate Normal | 88 | 32 | 32.4 | 9.4582 | 0.40129 | 0.39985
Bivariate Lognormal | 4.4363 | 0.30365 | 3.4536 | 0.25584 | 0.42912 | 0.41884
Normal Cost, Lognormal Schedule | 99.9994 | 31.5273 | 3.431 | 0.25584 | 0.26293 | 0.4537
Lognormal Cost, Normal Schedule | 4.4124 | 0.30365 | 33.145 | 9.4582 | 0.46015 | 0.36975